## Initiatives
[30 empty] | General information | BEFORE PRE-STUDY PDI |  |  | Before Pre-study PDI | PRE-STUDY RELATED INFORMATION | [8 empty] | Pre-study related info. |  | PROJECT RELATED INFORMATION | [6 empty] | Project related info. | TIME & COST |  | Time & Cost | DEPENDENCIES | [5 empty] | Dependencies | CHANGE IMPACT | [8 empty] | Change Impact | RUNNING INFORMATION | [13 empty] | Running Information
ID | Initiative | Initiative Status | Expected Start FY | Expected Start date | Expected End FY | Expected End date | Initiative Type | Initiative Category | Program | MHS Functionality | Project Objective | MHS TP Objective | MHS TP PDI covered | MHS TP Scope covered | Additional scope approved (If applicable) | IWOW Process LEVEL 0 | Process Owner | Process Leader | Demand Areas LEVEL 0 | Solution area | Business Architect Manager (BAM) | IT Architect Manager (ITAM) | Chairman for SG | Sponsor for SG | MHS TP Representative in SG | Orderer | Owner | Business Project Manager | IT Project manager |  | Anchored with applicable forums | IF YES OR NO- WHICH FORUMS | Budget Secured (Clarity) |  | MHS TP SG Approval of starting up Prestudy | Prestudy approach approved | Approved Pre-study PDI in applicable forums | Pre-study IT Blueprint conducted | SG for Prestudy appointed | Funds Secured for Prestudy | Business study conducted | Solution study conducted | Pre-study Report approved by Pre-study SG |  | Pre-study Report approved by MHS TP SG | Approved PDI & GPA for project in applicable forums | Approved GPA & PDI for project in Project SG | Approved PDI & GPA for projec by MHS TP SG | Project IT Blueprint conducted | Funds Secured for Project | SG for project appointed | Mapped dependencies to IWOW (all levels) |  | HL Cost Estimation Total Initative | HL Time Estimation total initative |  | Mapped dependencies to other projects | Mapping dependencies to Process conducted | Mapping dependencies to Organisation conducted | Where in the organisation(department) does the dependency lie | Mapping dependencies to technology conducted | Dependent on technology |  | Process | WHEN | Organisation | Number of impacting end user | WHEN | Technology Change impact system development | WHEN | Information Change impact for user | WHEN |  | "Gut feeling" | Important milestone | Planned DP1 | Actual DP1 | TP Critical DP1 | Planned DP3 | Actual DP3 | TP Critical DP3 | Planned DP6 | Actual DP6 | TP Critical DP6 | Planned DP8 | Actual DP8 | TP Critical DP8 |  | Old Comments | Comments 23.01.2015 | Comments 11.02.2015/17.02.2015
NTV01 | One COS | Closed | n/a | - | n/a | - | Project | Dependency | Planned Business | Sales Order Management & Reservations |  |  |  |  | n/a | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Range&Supply | TBD | Göran Johansson | Jacob Nordegren |  |  |  | Franklin Post |  | Johanna Arnell | Lena Bengtsdotter |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES |  | YES | YES | YES |  |  | n/a | [6 empty] | YES | YES | [6 empty] | NONE |  |  |  |  | n/a | n/a | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
NTV02 | SAREC+ | Roll out | n/a | - | FY16 - T3 | 31.08.2016 | Project | Dependency | Planned Business | Finance Management | New standards, routines and tools for | Take over all cash reconcilliation and business accounting |  |  | n/a | Perform and report financial activities | Martin van Dam | TBD | Supporting | Business Administration or N/A? | Karsten Stiegler |  |  | Frank Verboven | n/a | Ruben de Jong | Eva Alfredsson | Johan Green | Klaudius Mainka |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a |  |  |  | n/a | YES | YES |  |  | n/a | [6 empty] | YES | YES | [6 empty] | NONE | [6 empty] | PTT: 2014.01.02 | PTT: 2014.01.02 | n/a | PTT: 2015.01.05 |  |  | PTT: 2015.11.30
NTV03 | POS Upgrade | Roll out | n/a | - | FY15 - T3 | 31.08.2015 | Project | Dependency | Planned Business | Cash & Credit Mgmt | One global payment system | Take over all cash management responsibility and remove Calypso/IBM4690 solutions |  |  | n/a | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) | Monica Persdotter-Holmsvik | Retail & Expansions |  | Per Råborg | Håkan Andersson | Fredrik Axén | Fredrik Axén | Fredrik Axén | Johanna Donner | Johanna Donner | Magnus Hedlund | Kristian Wahlgren |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES |  | YES | YES | YES |  |  | n/a | [6 empty] | YES | YES | [6 empty] | NONE |  |  |  |  | N/A | N/A | PTT: 2010.03.05 | PPO: 2010.03.31 | N/A | PPO: 2012.12.17 PTT: 2012.12.27 | PPO: 2012.12.17 PTT: 2012.12.27 | N/A | PTT: 2013.09.01 | PTT: 2013.12.20 | N/A | PPO: 2015.08.28 PTT: 2015.08.30 |  | Emil: 2015.08.30 |  | India, Romania and Croatia not part of project but needs to be moved to TP.NET before dependent projects can proceed.
NTV04 | STMS Delivery Planning | Running | n/a | - | FY15 - T3 | 31.08.2015 | Project | Impacting | Planned Business | (affect) SGF | Expectation is to not add on logic in MHS unless it clearly takes us towards a target solution | Replacing CNS, new foundation for the delivery area in IKEA |  |  | n/a | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Range&Supply | Order & Delivery | Göran Johansson | Jacob Nordegren | Davide Urani | Lars Gunnarsson | Melaine van Der Toorn Vritjhoff | Marcus Baumgartner & Paulo Cinelli |  | Henrik Bjurman | Ulf Zachrisson |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES | YES | YES | YES | YES |  |  | n/a | n/a | [5 empty] | YES | YES | [6 empty] | M | FY15/T2-T3 |  |  |  | N/A | N/A | LDI: 2014.02.07 PTT: 2014.02.12 | LDI: 2014.02.07 PTT: 2014.02.12 | n/a | LDI: 2015.01.31 PTT: 2015.01.30 | PPI: 2015.01.31 PTT:2015.01.30 |  |  |  |  | PPI:2015.08.31 |  |  |  | Their goal is to not impact MHS more then reusing existing CNS interface. |  | Status: The MHS-team has no resources currently to support them in the capacity needed. It is very slow progress right now and it is difficult making things happen. We need to take more control and see what is most important and urgent from an MHS-perspective.
NTV05 | PinS | Roll out | n/a | - | n/a | - | Project | Dependency | Planned Business | SGF | Rollout Picking in Store to all stores | Complete rollout of PinS and sales order |  |  | n/a | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Range&Supply | Order & Delivery | Göran Johansson | Jacob Nordegren | Martin Fachinger | Melanie van Der Toorn Vritjhoff | n/a | Martin Fachinger |  | Magnus Anderberg | Jonatan Lindqvist |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES | YES | YES | YES | YES |  |  | n/a | [6 empty] | n/a | n/a | [6 empty] | NONE |  |  |  |  | n/a | n/a | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | Expected to be rolled out during FY14 |  | Status: Confirmed date to go live week 18.
NTV06 | Centiro FR | Closed | n/a | - | n/a | - | Project | Dependency | Planned Business | Sales Order Management & Reservations | Rollout centiro in France | Remove all HODS usage in MHS and enable cleanup of old customer order logic in MHS |  |  | n/a | Plan Sales and Supply | Marcus Baumgartner | Marie Klasson | Range&Supply | TBD | Göran Johansson | Jacob Nordegren |  | Lars Gunnarsson |  |  | Rickard Klasson | Magnus Anderberg | n/a |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [8 empty] | n/a | [6 empty] | YES | YES | [6 empty] | NONE | [6 empty] | Ongoing | [8 empty] | Emil: 2015.12.01 (France Dec 2014) |  |  |  | This together with OneCOS and PinS enables removal of customer order mgmt Jean-Luc Delfesc for France
NTV07 | Quality Deviation | Running | n/a | - | FY18 - T3 | 2015.08.31 | Project | Dependency | Planned Business | Range | Capture and handle quality deviations and handle sales stops... | Adds sales stop integration to MHS and disable Sales stop administration in MHS |  |  | n/a | Plan Sales and Supply | Marcus Baumgartner | Marie Klasson | Range&Supply | Purchasing & Supplier Development | Göran Johansson | Jacob Nordegren | Karen Pflug | Lars Gunnarsson | n/a | Karen Pflug |  | Karl Bergfors | Camilla Larsson |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES | YES | YES | YES | YES |  |  | n/a | [6 empty] | n/a | n/a | [6 empty] | L | FY15/T3-FY16-T1 |  |  |  | N/A | N/A | PPI: 2013.07.01 PTT: 2013.07.01 | PPI: 2013.07.01 PTT: 2013.07.01 | N/A | PPI: 2014.12.17 PTT: 2014.12.17 | [5 empty] | PPI: 2017.03.31 | PPI: 2018.08.30 (Forecast) |  |  | Introduces sales stops on a lower level in MHS then today and in more flows in the store. |  | Status: To be filled in in more detal. (Both Impacting och dependency)
NTV08 | New shortage handling Prestudy | Running | FY15 - T2 | 2015.01.01 | FY15 - T3 | 2015.08.31 | Pre-Study | Impacting | Planned Business | n/a | New way of calculating and act on shortages. New shortage reasons that are more precise | Align with MHS TP in prestudy and not add major development to MHS |  |  | n/a | Plan Sales and Supply | Marcus Baumgartner | Marie Klasson | Range&Supply |  | Göran Johansson | Jacob Nordegren |  | Lars Gunnarsson |  |  |  | Siv Bennhagen |  |  |  | n/a | [13 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [33 empty] | The actual project will put new requirements to SGF and SLM parts of MHS
NTV09 | One Common Replenishment | Not Started | FY16 -T1 | 2015.09.01 | FY 17 - T3 | 2017.08.31 | Project | Dependency | Planned Business | Forecast & Safety Stock | Move the replenishment logic to JDA and in this move out Forecasting and Safety stock from MHS | Removes all forecasting and safety stock from MHS so that SRS part of MHS can be closed |  |  | n/a | Plan Sales and Supply | Marcus Baumgartner | Marie Klasson | Range&Supply | TBD | Göran Johansson | Jacob Nordegren |  | Lars Gunnarsson |  |  | Lars Gunnarsson | Björn Westerberg | tbd |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [8 empty] | n/a | [6 empty] | YES | YES | [13 empty] | Emil: 2015.09.01 | [8 empty] | Emil: 2017.08.31 |  |  |  | Planning for PoC in Älmhult and Malmö store. Estimated to 3 years assuming that first estimation on 3 years to be rolled out can be shortened to 2,5 and have 6 month for cleanup... |  | Status: Defining scope in progress but there is no real pre-study. Eva-Lotta has had a meeting with Pär Gustafsson and Björn Westerberg and the project seems to be on track. Risk: We might need to take on OCR but if we do so we will peal of whatd not in MHS scope and put our demands on it. It might even be best if MHS takes it to secure priority. Give them a deadline to reach a result - programme formulation or we will go to a Plan B. Action: STEFAN will book a meeting with EVA-LOTTA and STEVE to disucss this.
NTV10 | DWP | Running | FY15 - T1 | 2015.01.01 | FY15 - T3 | 2015.08.31 | Project | Impacting | Planned Business | SGF | Improve data quality and get better accuracy in DWP information | Consider MHS TP in the design by splitting need in terms of SGF, SLM and other components. |  |  | n/a | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Range&Supply | Handling & Storage | Göran Johansson | Jacob Nordegren | Werner Hölter | Lars Gunnarsson |  | Werner Hölter |  | Tobias Rehnström | Peter Nordström |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [8 empty] | n/a | n/a | [5 empty] | n/a | n/a | [13 empty] | PPI: 2014.06.08 | PPI: 2014.06.08 | N/A | PPI: 2014.12.05 Emil: 2014.12.15 | PPI: 2014.12.05 | N/A | PPI: 2015.04.30 | PPI: 2015.04.30 |  | PPI: 2015.08.31 Emil: 2015.05.30 | PPI: 2015.08.31 |  |  | Redesign of the DWP information flow
NTV11 | Future BI Landscape | Running | FY14 - T1 | 2013.09.01 | FY16-T2 | 2016.04.30 | Project | Impacting | Planned Business | Reporting | Establish the Future BI platform including an enhanced CLA, common landing area for all incomming and outgoing data and IDSS, a common Enterprize Data Warehouse(EDW) in the form of and IKEA decision support system envisioned to serve all of IKEA with data for BI reporting and Analytic purposes. Develop BI tailored processes to support efficient Life cycle managmement of the asset. Implement the solutions currently running on legacy IBIS EDW like for like from an enduser perspective and based on their data need, form the basis for the future common data dimentions. In this work, secure that all data entering the CLA/IDSS platform adheres to Information Management policies. | To only fetch information from source system and not MHS. Utilize integration point for integration |  |  | n/a | Perform and report financial activities | Martin van Dam | TBD | Supporting | Business Performance | Karsten Stiegler | Sten Hansson | Don Peterson | Frank Verboven |  | Don Peterson | Anna Almqvist | Mikael Nordbeck | Carina Beckman |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES |  | YES | YES | YES |  |  | n/a | n/a | [5 empty] | YES | YES | [6 empty] | L | FY15/T3 | [5 empty] | PPI: 2013.04.17 PTT:2013.04.15 | PPI: 2013.04.17 PTT:2013.04.15 |  | PPI: 2014.02.03 PTT:2014.01.20 | PPI: 2014.02.05 PTT:2014.01.20 |  | PPI: 2015.12.31 PTT: 2015.10.31 | PPI: 2015.12.31 |  | PPI: 2016.02.15 PTT: 2016.02.15
NTV12 | Support Ticket Management Pre-Study | Not Started | FY15 - T3 | 2015.05.31 | FY16-T1 | 2016.12.31 | Pre-Study | Dependency | Planned Business | Return Management |  |  |  |  | n/a | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) | Monica Persdotter-Holmsvik | Retail & Expansions | TBD |  |  |  | Fredrik Axén |  |  | Peder Apelgren | tbd | tbd |  |  | n/a | [13 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [21 empty] | 2015.01.01 | [8 empty] | Emil: 2015.08.31 |  | Emil: 2015.04.30
NTV13 | Support Ticket Management Project | Not Started | FY16 -T1 | 2016.09.01 | FY 17 - T3 | 2017.08.31 | Project | Dependency | Planned Business | Return Management |  |  |  |  | n/a | Convert visitors to happy customers so they return again |  |  | Retail & Expansions | TBD |  |  |  | Fredrik Axén |  |  |  | tbd | tbd |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [8 empty] | n/a | [6 empty] | YES | YES |  | H | ? | H | 15000 | ? | H | FY16-FY17 | H | ? |  |  |  | Emil: 2015.08.31 | [12 empty] | Assumption is that it will be started FY16
NTV14 | Integrated Finance Platform | Running | FY15 - T1 | 2014.09.01 | FY20 - T3 | 2020.08.31 | Project/Program | Impacting | Planned Business | Finance Management |  | To minimize the needs of information from MHS |  |  | n/a | Perform and report financial activities |  |  | Supporting |  | Karsten Stiegler |  |  | Frank Verboven |  |  | Ines Bajalo | Rineke Renema |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [8 empty] | n/a | n/a | [5 empty] | n/a | n/a
NTV15 | Traceability | Not Started | FY16 - T1 | - |  | - | Project | Impacting | Planned Business | ALL |  |  |  |  | n/a | Plan Sales and Supply | Marcus Baumgartner | Marie Klasson | Range&Supply | TBD | Göran Johansson | Ingemar Rask |  | Lars Gunnarsson | [6 empty] | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [8 empty] | n/a | n/a | [5 empty] | n/a | n/a |  | ? | ? | ? | ? | ? | ? | ? | ? | ? | [12 empty] | ?
NTV16 | Multichannel Replenishment Prestudy (range information) | Closed | n/a | - | n/a | - | Pre-Study | Dependency | Planned Business | Forecast & Safety Stock |  | Range management |  |  | n/a | Plan Sales and Supply |  |  | Range&Supply | TBD | [25 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [29 empty] | FY14
NTV17 | SOM | Running | n/a | - | FY16 - T3 | 2016.08.31 | Project | Dependency | Multichannel Transformation Programme | Sales Order Management & Reservations | Initiative with purpose to develop and implement a total distribution solution for eCommerce | Remove MHS role in all orders with services |  |  | n/a | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Range&Supply | Order & Delivery | Göran Johansson | Jacob Nordegren | Helena Lindstedt | Matthias Wilm | Melaine van Der Toorn Vritjhoff | Björn Westerberg | Mathias Wilm | Jerry Andren | Anders Ekdahl |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES | YES | YES | YES | YES |  |  | n/a | [6 empty] | YES | YES | [6 empty] | L | FY16 |  |  |  | n/a | n/a | PPI: 2013.02.21 PTT: 2013.03.04 | PPI: 2013.03.04 | n/a | PPI: 2014.05.16 PTT: 2014.05.16 | PPI: 2014.05.16 | n/a | PPI: 2016.06.02 PTT: 2015.05.30 | PPI: 2016.06.02 |  | PPI: 2016.08.19 PTT: 2016.08.31 |  |  |  | Mainly adds functionality to different parts of MHS, but might remove some dependecies. |  | Status: Concern for "varuhusordrar" that might not be in scope. Do we need to adress this in our plan? Multichannel Channel Returns are driven by SOM. SOM's solution handels it and MCR makes the demands. We need to find out the scope of Sales Order Management eCom. Do we need to "isolate" them more to makes us less dependent on them? * EMIL has a meeting booked 9.03.2015 to find out the cost-framework and how this affects our scope. An extra effort needs to be made. * STEFAN needs to know status prior to 25.02.2015 Action: EMIL will book a meeting with CHRISTER and go through this and then inform STEFAN prior to 25.02.2015
NTV18 | Multichannel Logistic set up for stores | Running | n/a | - | FY16 - T3 | 2016.08.31 | Project | Impacting | Multichannel Transformation Programme | SGF | Integration of eCommerce solution to support click&collect and Remote Stores | Implement necessary for supporting click&collect & remote store. |  |  | n/a | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Retail & Expansions | N/A | Göran Johansson | Jacob Nordegren | Martin Fachinger | Matthias Wilm | n/a | Marcus Baumgartner | Martin Fachinger | Erwin Goldner | Marcus Jernvilde |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES | YES | YES | YES | YES |  |  | n/a | n/a | [5 empty] | YES | YES | [6 empty] | M | FY16 | [5 empty] | PPI: 2014.01.22 PTT: 2014.01.23 | PPI: 2014.01.22 |  | PPI: 2015.02.01 PTT: 2014.10.01 | [5 empty] | PPI: 2016.08.31 |  |  |  | Will add new functionality, mainly to SGF and Customer Order Picking. MFLU Solution could have big impact on MHS
NTV19 | Multichannel Returns Management | Running | n/a | - | FY16 - T3 | 2016.08.32 | Project | Impacting | Multichannel Transformation Programme | Return Management OR/AND SGF | Set solution and process for how to handle returns (internal and external) in a multi channel environment |  |  |  | n/a | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) | Monica Persdotter-Holmsvik | Retail & Expansions |  | Per Råborg | Håkan Andersson |  | Matthias Wilm |  |  | Monica Holmvik Perdotter | Torbjörn Andersson | tbd |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [8 empty] | n/a | n/a | [5 empty] | YES | YES | [6 empty] | M | FY15/T3 | [5 empty] | Ongoing | [12 empty] | Wave 4 is expected to be last with MHS impact from returns, could be moves to wave 5.
NTV20 | eCom Global Rollout Project | Running | n/a | - | FY17 - T3 | 2017.08.31 | Project | Dependency | Multichannel Transformation Programme | n/a | Define how to define the range in a multichannel environment | Rollout eCom solution to all countries with implementations of all the eCom projects |  |  | n/a | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Retail & Expansions |  | Matthias Wilm | Fredrik Åkerberg |  | Matthias Wilm | [6 empty] | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES | YES | YES | YES | YES |  |  | n/a | [14 empty] | NONE? | FY? | [6 empty] | PPO: 2014.02.17 |  | PPO: 2014.08.26 | PPO: 2015.05.28 | [10 empty] | Status: Trying to become as independent as possible
NTV21 | Local integration platform Pre-Study | Running | FY15-T1 | 2014.09.01 | FY15 - T2 | 2015.04.30 | Pre-Study | MHS TP | MHS Transformation Program | Integration | A solution that takes over MHS role as a local integration service is needed | To have a solution which MHS integrations can be moved to |  | Data routing | n/a | Secure IT Solutions | Paolo Cinello | Cecilia Karlsson/Thomas Frisk | Supporting |  | Per Råborg | Håkan Andersson | Magnus Persson | Marie Lindberg | Emil Nilsson |  | Kajsa Hofvendahl | Jonathan Lindqvist | Niklas Olsson |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [5 empty] | n/a | n/a | [13 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Emil: 2015.04.30 | Emil:2015.04.30 |  | This is not yet an initiative! |  | Status: Ongoing disucssions regarding details in scope and expectations. We need to know the status or we will set up an applicationforum. * EMIL has a meeting 19.02.2015 to address some of these issues. More meetings will follow. The outcome of this will inform us of necessary actions that needs to be taken.
NTV22 | Local integration platform | Not Started | FY16-T1 | 2015.09.31 | FY16-T3 | 2016.08.31 | Project | MHS TP | MHS Transformation Program | Integration | A solution that takes over MHS role as a local integration service is needed | To have a solution which MHS integrations can be moved to |  | Data routing |  | Secure IT Solutions | Paolo Cinello | Cecilia Karlsson/Thomas Frisk | Supporting | TBD | Per Råborg | Håkan Andersson |  | Marie Lindberg |  |  | Kajsa Hofvendahl | n/a | Niklas Olsson | [34 empty] | L | FY16/T3 | L | 500 | FY16 | H | FY15-FY16 | L | FY16 | [14 empty] | Emil: 2016.08.31 |  |  | Status: Ongoing - delayed on time. Estimation on project. Need to make resource assumption. Concern usigt of existing LIP in store. Does communication need to be sent out? (BN/ITPM)
NTV23 | Cash Management Pre Study | Not Started | FY16 -T1 | 2015.09.01 | FY16 -T1 | 2015.12.31 | Pre-Study | MHS TP | MHS Transformation Program | Cash & Credit Mgmt | Close down usage of all cash reconcilliation in MHS (and store point for non food sales) and cleanup the code | No cash reconcilliation code in MHS and MHS being indepent of full receipt information |  |  | n/a | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) | Monica Persdotter-Holmsvik | Retail & Expansions | TBD |  |  |  | Fredrik Axén |  |  | Johanna Donner | tbd | [17 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [34 empty] | Status: Should we start up Prestudy earlier? Action: Will approach Johanna in March -15 | Action: Change name to Cash Management in the Roadmap until next meeting (EMIL) Secure Johanna is secure and align budget request before 25/2 (STEFAN) Appoach owner for startup discussion in March-15 (EVA-LOTTA) (from a technical perspective we can start up directly but from a resource perspective that might be a constraint)
NTV24 | Cash Management | Not Started | FY16-T2 | 2016.01.01 | FY17-T2 | 2017.04.30 | Project | MHS TP | MHS Transformation Program | Cash & Credit Mgmt | Close down usage of all cash reconcilliation in MHS (and store point for non food sales) and cleanup the code | No cash reconcilliation code in MHS and MHS being indepent of full receipt information |  |  |  | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) | Monica Persdotter-Holmsvik | Retail & Expansions | TBD |  |  |  | Fredrik Axén |  |  | Johanna Donner | tbd |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | YES | YES |  | L | FY16/T3 | M | 3000 | FY16/T3 | M | FY16 | M | FY16/T3 |  |  |  | Emil: 2015.09.01 | [8 empty] | Emil: 2016.08.31 |  |  |  | Can be started before POS Upgrade is rolled out by deactiving functionality for stores already rolled out. But can not be confirmed as done until it is fully rolled out | Status: Start Close Cash Mgmt Project. Action: Start-up meeting with process owner/demand owner. | Status: Investigating if changing the scope the MHS Secure Reporting to exclude the Cash Management reports since they are going to be moved out with Cash Management FY16 anyway. This will happen during T2 FY15 (IOANNIS)
NTV25 | Customer Financing Re-Design Pre-Study | Running | FY15-T1 | 2014.09.01 | FY15 - T3 | 2015.08.31 | Pre-Study | MHS TP | MHS Transformation Program | Cash & Credit Mgmt |  |  |  |  | n/a | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) | Monica Persdotter-Holmsvik | Retail & Expansions |  |  |  |  | Fredrik Axén |  |  | Johanna Donner | Andreas Tasdelen | n/a | [16 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [20 empty] | Emil: 2015.01.01 |  |  | Emil: 2015.03.01 | [5 empty] | Emil: 2015.08.15 |  | End FY16 |  | IKANO NO terminated for business and private customer. IKANO SE will be tought to terminate IKANO DK still has RIMS customers DE - Ikano behind RIMS Rest - RIMS Ska ha möte närmaste månad om credit management ska dödas. |  | Status: Change name on roadmap to Customer Financing Re-Design Pre-Study until next meeting (EMIL) Release and finally confirm approavl of PDI and relase of funds at MHSTP SG 10/3 (EVALOTTA) Action: Keep close control of design related to Business Credit initative via: * Involved in reviewing the bluepringt along the prestudy and before DP1 (CHRISTER) RISK: Potetnial risk related to change of IT-resource to be followed up during week 7-8 (IOANNIS)
NTV26 | Customer Financing Re-Design Project | Not Started | FY16-T1 | 2015.09.01 | FY16-T3 | 2016.08.31 | Project | MHS TP | MHS Transformation Program | Cash & Credit Mgmt | Remove all credit management for IKEA business customer cards and family cards from MHS. | MHS has nothing to do with consumer finance or business credit any more |  |  |  | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) | Monica Persdotter-Holmsvik | Retail & Expansions | TBD | Karsten Stiegler |  |  | Fredrik Axén |  |  | Johanna Donner | tbd | n/a |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | YES | YES |  | M | FY16/T3 | L | 3000 | FY16/T3 | M | FY16 | M | FY16/T? |  |  |  | Emil: 2015.09.01 | [10 empty] | Emil: 2016.08.31 |  | IKANO NO terminated for business and private customer. IKANO SE will be tought to terminate IKANO DK still has RIMS customers DE - Ikano behind RIMS Rest - RIMS Ska ha möte närmaste månad om credit management ska dödas. |  | Action: Change name on roadmap to Customer Financing Re-Design Pre-Study until next meeting (EMIL)
NTV27 | Receipt Management Pre-Study | Not Started | FY16-T1 | 2015.09.01 | FY16 - T2 | 2016.04.30 | Pre-Study | MHS TP | MHS Transformation Program | Cash & Credit Mgmt |  |  |  |  | n/a | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) | Monica Persdotter-Holmsvik | Retail & Expansions | TBD |  |  |  | Fredrik Axén |  |  | Johanna Donner | TBD | tbd | [16 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [20 empty] | 2016.01.01 | [8 empty] | Emil: 2016.08.31 |  | Emil: 2016.08.31 |  |  | Status: Closely linked to Cash Mgmt. Need to follow up.
NTV28 | Receipt Management/Integration move out | Not Started | FY17 - T1 | 2016.09.01 | FY18 - T3 | 2018.08.30 | Project | MHS TP | MHS Transformation Program | Cash & Credit Mgmt | Receipt information , payment information, family card sales, etc has to be moved out of MHS unless needed by SGF, SLM and Customer Order Picking | MHS only received the receipt information needed by SGF, SLM and Customer Order Picking |  |  |  | Convert visitors to happy customers so they return again |  | Monica Persdotter-Holmsvik | Retail & Expansions | TBD | Per Råborg | Håkan Andersson |  | Fredrik Axén |  |  |  | tbd | tbd |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | YES | YES |  | ? | FY17-FY18 | ? | ? | FY18 | H | FY17-FY18 | H | FY18 |  |  |  | Emil: 2016.09.01 | [8 empty] | Emil: 2018.08.31 |  | Emil: 2016.08.31
NTV29 | Customer Order Management Clean-up Pre-study | Not Started | FY15-T2 | 2015.01.01 | FY15-T3 | 2015.08.31 | Pre-Study | MHS TP | MHS Transformation Program | Sales Order Management & Reservations | Move all CCD and old C&C order structures, report and screens from MHS. Secure that WinMHS is really closed down. | Cleanup old C&C and CCD order management in MHS. Also remove DB server. |  |  | n/a | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Retail & Expansions | TBD |  |  |  | Lars Gunnarsson |  | MHS TP | Rickard Klasson | [18 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [20 empty] | Emil:2015.04.01 | [8 empty] | 2015.08.31 |  |  |  |  | Status: Adress ownership. The ambition is to start up the prestudy March-Maj and the project in June. Action: Meeting next w.5 with Melanie & Lasse | Status: Awaiting EVA-LOTTA and therefore do not know the start date. IT can start with the technical analysis. Should be run in Rikard Klassons area. Risk: Not getting a hold of the necessary people to run the pre-study. It is very technical so there might not be a need for a PM - and if there is a PM she/he should have both a technical and a business background. However, might work with a business analyst Action: Start up technical bit (HENRIK)
NTV30 | Customer Order Management Clean- up | Not Started | FY15 - T3 | 2015.05.31 | FY16-T2 | 2016.04.30 | Project | MHS TP | MHS Transformation Program | Sales Order Management & Reservations | Move all CCD and old C&C order structures, report and screens from MHS. Secure that WinMHS is really closed down. | Cleanup old C&C and CCD order management in MHS. Also remove DB server. |  |  |  | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Retail & Expansions | TBD | Göran Johansson | Håkan Andersson |  | Lars Gunnarsson |  | MHS TP | Rickard Klasson | n/a | n/a |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | YES | YES |  | L | FY16/T2-T3? | L | ? | FY16/T2-T3 | M | FY16 | L | FY16/T2-T3? |  |  |  | Emil: 2015.09.01 | [8 empty] | Emil: 2016.08.31 |  |  |  | Includes both CCD and old C&C management part. Risk that PinS project leaves few stores, which must be done for this initative to be started
NTV31 | Local Pricing Management - Project | Not Started | FY15 - T2 | 2015.01.01 | FY16 - T3 | 2016.08.31 | Project | MHS TP | MHS Transformation Program | Range & Pricing | [5 empty] | Develop a complete and relevant home furnishing offer | Kristofer Magneteg | Peter Klinkert | Range&Supply | TBD |  |  |  | Pär Gustafsson |  |  | Rickard Klasson | tbd |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | YES | YES |  | M | FY17? | M | 1500 | FY17? | M | FY15/T3-FY16 | L | FY17? |  |  |  | Emil: 2015.04.01 | [10 empty] | Emil: 2016.08.31
NTV32 | Local pricing management Pre-Study | Running | FY15- T1 | 2014.09.01 | FY15-T2 | 2015.04.30 | Pre-Study | MHS TP | MHS Transformation Program | Range & Pricing |  |  |  |  | n/a | Develop a complete and relevant home furnishing offer | Kristofer Magneteg | Peter Klinkert | Range&Supply |  |  |  |  | Pär Gustafsson |  |  | Rickard Klasson | Ingela Ludvigsson (MHS Scope) |  |  | YES |  | YES |  | YES | YES | YES |  | YES | YES | [5 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [5 empty] | YES | YES | [13 empty] | 2014.11.24 | [8 empty] | Emil: 2015.01.31 | Emil: 2015.01.31 | Emil: 2015.02.28 |  | Prestudy Sep -14, project jan-15. VAT management partly in pricing scope (also in finance Eva A) | Status: Ongoing - delayed on time | Status: Plan is to ready for preparing DP1, mid march, DP1 planned end of March Current risks on radar is the LIP which might not provide the functionality needed but also the LIP timeplan related to initative timeplan Action: Support prestudy with Vendor management during w.7-8 (IOANNIS) Support securing MHS ITSA, during w. 7-8 (IOANNIS) Support prestudy with assigmenet of PM to be in place for define phase startup. Start up discussions week 7-8 (IOANNIS) Clarifying the LIP functionallity related to initative needs (EMIL) Clarifying the LIP timeplan related to initative timeplan (EMIL) Provide Ingela with information about MHSTP SG Approval steps (STEFAN)
NTV33 | Store Range Management move out | Not Started | FY17 - T1 | 2016.09.01 | FY18 - T3 | 2018.08.31 | Project | MHS TP | MHS Transformation Program | Range & Pricing | What system should steer what is possible to sell in a store in the future. All rules and information flow around life cycle for articles in a store must be handled. | Remove MHS as the owner of range available for selling. Move out item attributes set in MHS |  |  |  | Develop a complete and relevant home furnishing offer | Kristofer Magneteg | Peter Klinkert | Range&Supply | Retail | Göran Johansson | Håkan Andersson |  | Lars Gunnarsson |  |  | Rickard Klasson | tbd |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | YES | YES |  | ? | ? | ? | ? | ? | H | FY17-FY18 | M |  |  |  |  | Emil: 2016.09.01 | [8 empty] | Emil: 2018.08.31 |  |  |  | The more move out initiatives that are done, the easier this one will be
NTV34 | Reporting Pre-Study | Closed | FY14 - April | - | FY14 (2014-07-11) | - | Pre-Study | MHS TP | MHS Transformation Program | Reporting |  |  |  |  | n/a | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) | Monica Persdotter-Holmsvik | Retail & Expansions | TBD |  |  |  | Mikael Andersson |  |  | mikael Andersson | Catarina Dehn | n/a | [16 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [5 empty] | YES | YES
NTV35 | Secure Reporting | Running | FY15-T1 | 2014.09.01 | FY16 -T2 | 2016.04.30 | Project | MHS TP | MHS Transformation Program | Reporting | [5 empty] | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) | Monica Persdotter-Holmsvik | Retail & Expansions | Retail |  |  |  | Mikael Andersson | Mikael Andersson |  | mikael Andersson | Catarina Dehn |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES | YES | YES | YES | YES | [9 empty] | YES | YES |  | L | FY16/T2 | M | 15000 | FY16/T2 | M | FY15/T2-FY16/T2 | H | FY16/T? |  |  |  | PPO: 2014.11.04 | PPO: 2014.11.13 |  | PPO: 2015.01.31 | [5 empty] | PPO: 2015.12.31 |  | Emil: Emil: 2016.05.31 |  | Very important to know the data need in a future logistic system and to minimize the information need in MHS. High impact on local solutions | Status: Need to follow up scope Secure approved released funds in MHS TP SG Actions: EN and CS need to have an meeting before SG to secure alignment. | Status: Heading towards a DP3 in march. Approal process sorted out and anchored with MHSTP SG Chair, Anders G considering to request a delay of DP3 due to lack of non-functional requirements impacting scope, cost & time. Due to "clean up" activities not clearly defined in the PDI there is a risk that the project will try to scope out this activity Actions: Looking in to potential to take out reports and put in to iPOS. To be decided w7 (IOANNIS) Managing IT resource situation, week 7 (IOANNIS) Rel to Anders request investigate CAPs view of this and their commitment related to perfomance requirments. To be clarified week 7 and further actions to be taken accordingly to identified situation (IOANNIS) Secure Clean up stays within the project scope, to be clarified during week 7-8 (HENRIK)
NTV36 | Tax 4 orders | Running | n/a | - | FY15 - T3 | 2015.08.31 | Project | Dependency | eCommerce Program | Tax Information & Calculation | Tax 4 orders will secure a correct taxtreatment of all sales and returns based on customer orders. | Unclear - According to eCom there is a small dependency. |  |  |  | Perform and Report financial activities |  |  | Supporting | Business Administration |  |  | Jan Messen | Mattias Wilm |  | Eva Alfredsson |  | Eva Alfredsson/Bastian Kleinschmidt |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | YES | YES | YES | YES | YES | YES | YES | [16 empty] | NONE | [6 empty] | PPI: 2014.07.23 | PPI: 2014.07.23 |  | PPI: 2015.01.30
NTV37 | TAX Information and Calculation Pre-Study | Closed | n/a | - | n/a | - | Pre-Study | MHS TP | MHS Transformation Program | Tax Information & Calculation |  |  |  |  | n/a | Perform and Report financial activities | Martin van Dam | TBD | Supporting | TBD |  |  |  | Frank Verboven |  |  |  | tbd | n/a | [16 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [5 empty] | YES | YES | [13 empty] | Emil: 2014.09.01 | [8 empty] | Emil: 2015.01.01
NTV38 | Store Logistic SLM/SGF Pre-Study | Running | FY15-T1 | 2014.09.01 | FY15-T2 | 2015.04.30 | Pre-Study | MHS TP | MHS Transformation Program | SLM/SGF | Find the target for SGF, CPS and Recovery part in MHS, should go hand in hand with SLM Prestudy | Define the target for SLM, SGF, Customer Order Picking and Recovery management |  |  | n/a | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Range&Supply |  | Göran Johansson | Jacob Nordegren |  | Lars Gunnarsson | Pär Gustafsson, Emil Nilsson, Lars Gunnarsson |  |  | Taisto Tapani |  |  | YES |  | YES |  | YES | YES | YES |  | YES | YES | [5 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [5 empty] | YES | YES | [13 empty] | Emil: 2014.12.01 |  |  | Emil: 2014.01.15 | [5 empty] | Emil: 2015.04.10 |  | Emil: 2015.04.10 |  | Rikard Klasson will own the prestudy. PDI to be ready Sept 15 |  | Status: Delayed. Taisto Tapiani will come back with a new plan week 9.
NTV39 | Sales Location Management move out | Not Started | FY18 - T1 | 2017.09.01 | FY22 - T3 | 2022.08.31 | Project | MHS TP | MHS Transformation Program | SLM | [5 empty] | Deliver products, services and related information to all customers |  |  | Range&Supply | TBD |  |  |  | Pär Gustafsson |  |  |  | Taisto Tapani |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | YES | YES |  | H | FY18-? | H | 15000 | FY18-? | H | FY18-? | H | FY18-?
NTV40 | Store Logistic Operation move out | Not Started | FY18 - T1 | 2017.09.02 | FY22 - T3 | 2022.08.32 | Project | MHS TP | MHS Transformation Program | SGF | Implement target for SGF, CPS and Recovery and remove it from OpenVMS | Move SLM, SGF, Customer Order Picking and Recovery management from the OpenVMS platform to the defined target |  |  |  | Deliver products, services and related information to all customers | Marcus Baumgartner | Björn Westerberg | Range&Supply | TBD | Göran Johansson | Jacob Nordegren |  | Melanie van Der Toorn Vritjhoff |  |  |  | tbd |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | YES | YES |  | H | FY18-? | H | 30000 | FY18-? | H | FY18-? | H | FY18-?
NTV41 | Secure Local Solutions | Not Running | FY15 - T2 | 2015.01.01 | FY15-T3 | 2015.08.31 | Project/Activity -TBD | MHS TP | MHS Transformation Program | Local Solutions | Identify local solutions with MHS impact and secure local solutions by adressing them as not supported or as 'approved' by providing APIs that will last beyond MHS move outs. | Secure all local solutions identified in 'Identify Local Solutions'. Either decomission or change data source |  |  |  | Secure IT Solutions | Paolo Cinello | Cecilia Karlsson/Thomas Frisk | Supporting | Same supporting |  |  |  | Mikael Andersson | Mikael Andersson or Marie? | Fredrik Axén | Marc Peeters | tbd |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | YES | YES |  | M | FY16/T2 | M | 500 | FY16/T2 | NONE | N/A | NONE | N/A |  |  |  | Emil: 2015.02.01 | [13 empty] | Status: MHS TP has a dependency to Marc Peeters. MHS TP needs information regarding how and what in MHS is integrated in the overall initative from Marc Peters. Actions: Follow-up meeting with MP (HENRIK) | Status PDI anchored with Marc who will bounce this with his IT Matrix week 9 anr report back to MHSTP 3/3. Actions Propose to move this initative to Core & IT in roadmap (EMIL) Identify profile for PM needed during w 7-8 (HENRIK) Scote for and assign PM to be in place start T3, 2015 (EVALOTTA) Finalize PDI and anchored with key stakeholders by week 10 (HENRIK) Anchor and release funds fo the prestudy at MHSTP SG 10/3 (EVALOTTA)
NTV42 | Proof of Concept | Running | n/a | - | FY15-T2 | 2015.04.30 | Activity | MHS TP | MHS Transformation Program | Infrastructure | [5 empty] | Secure IT Solutions | Paolo Cinello | Cecilia Karlsson/Thomas Frisk | Supporting |  |  |  |  | Petra ten Berg |  |  |  | N/A |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | n/a | n/a |  | NONE | N/A | NONE | N/A | N/A | NONE | N/A | NONE | N/A |  |  | PoC ready 15.03.31 | Emil: 2014.09.01 | [8 empty] | Emil: 2015.03.30 |  | Emil: 2015.03.30 |  | based on assumption that we migrate to a linux platform
NTV43 | MHS Initial cleanup | Closed | FY14 - T1 | - | FY15-T3 | - | Activity | MHS TP | MHS Transformation Program | Core=ALL | Cleanup database and code that is no longer used in MHS. Most likely not driven as a project | To get rid of unused information in the database to simplify analysis, move out and potential migration |  |  |  | Secure IT Solutions | Paolo Cinello | Cecilia Karlsson/Thomas Frisk | Supporting |  |  |  |  | Petra ten Berg | [6 empty] | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | n/a | n/a |  | NONE | N/A | NONE | N/A | N/A | L | FY15 | L | FY15 |  |  |  | Emil: 2014.09.01 | [8 empty] | Emil: 2015.08.31 |  | 2015.08.31
NTV44 | Standardize and prepare | Running | FY15 - T1 | 2014.09.01 | FY20 - T3 | 2020.08.31 | Activity | MHS TP | MHS Transformation Program | Core=ALL | Plaftorm Independent GUI, move to C++, other outcomes from PoC to simplify a future migration | To consolidate business logic and simplify move out and migration |  |  |  | Secure IT Solutions | Paolo Cinello | Cecilia Karlsson/Thomas Frisk | Supporting |  |  |  |  | Petra ten Berg |  |  |  | N/A |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | n/a | n/a |  | ? | ? | ? | ? | ? | L | FY15-FY20 | L | ? | [14 empty] | n/a |  | ????? |  | Status: Re-evaluate Standardize and Prepare. Action: STEFAN will book a meeting with CHRISTER, IOANNIS, HENRIK and EMIL.
NTV45 | Remove MHS system dependencies Pre-Study | Not Started | FY16-T1 | 2015.09.01 | FY16-T2 | 2016.04.30 | Pre-Study | MHS TP | MHS Transformation Program | Integration | Removing system dependencies from MHS, e.g. PTAG and VTS where there are other data sources possible for the information. Sales order (pure full serve not handled by SOM), etc | Remove system dependencies with only technical dependencies to MHS |  |  | n/a | Secure IT Solutions | Paolo Cinello | Cecilia Karlsson/Thomas Frisk | ? | TBD |  |  |  | Petra ten Berg |  |  |  | tbd | [17 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [29 empty] | Emil: 2016.08.31
NTV46 | Remove MHS system dependencies | Not Started | FY16-T3 | 2016.05.01 | FY17-T3 | 2017.08.31 | Project | MHS TP | MHS Transformation Program | Integration | Removing system dependencies from MHS, e.g. PTAG and VTS where there are other data sources possible for the information. Sales order (pure full serve not handled by SOM), etc | Remove system dependencies with only technical dependencies to MHS |  |  |  | Secure IT Solutions | Paolo Cinello | Cecilia Karlsson/Thomas Frisk | ? | TBD |  |  |  | Petra ten Berg |  |  |  | tbd |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [15 empty] | YES | YES |  | ? | ? | ? | ? | ? | H | FY17 | L | ? | [16 empty] | With a Local Integration Platform, more work can be done in this area
NTV47 | Store Range Management Pre-study | Not Started | FY16 T2 | 2016.01.01 | FY16 T3 | 2016.08.31 | Pre-Study | MHS TP | MHS Transformation Program | Range & Pricing | What system should steer what is possible to sell in a store in the future. All rules and information flow around life cycle for articles in a store must be handled. | Remove MHS as the owner of range available for selling. Move out item attributes set in MHS |  |  | n/a | Develop a complete and relevant home furnishing offer | Kristofer Magneteg | Peter Klinkert | Range&Supply | Retail | Göran Johansson | Håkan Andersson |  | Lars Gunnarsson |  |  | Rickard Klasson | tbd |  |  | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | n/a | [29 empty] | Emil: 2016.08.31 |  |  |  |  | Status: Start up discussion Action: Meeting with owners | Status: Fuzzy - started but no assumed targets.
NTV48 | Remove SG 87 | Running | FY15-T2 | 2015.01.01 | FY16-T1 | 2015.12.31 | Activity | Dependency | MHS Transformation Program | Tax Information & Calculation | Remove need to use a specific item for handling pre payment information at Ikea | Remove MHS logic connected to pre payment item |  |  |  | Perform and Report financial activities | Martin van Dam | TBD | Supporting |  | Karsten Stiegler |  |  | Frank Verboven | [6 empty] | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [18 empty] | L | FY16/T? | L | 1000? | FY16/T? | M | FY15/T2-FY16 | M | FY16/T? | [14 empty] | 2017.08.31
NTV49 | Static Retail Tax Information | Not Started | FY15-T3 | 2015.05.01 | FY16 -T3 | 2016.08.31 | Project/Activity -TBD | MHS TP | MHS Transformation Program | Tax Information & Calculation | To have one place for administrating TAX and one common source for this information | Remove TAX Administration and integration from MHS. Remove Currency data. |  |  |  | Perform and Report financial activities | Martin van Dam | TBD | Supporting | Finance | Karsten Stiegler |  |  | Frank Verboven | [6 empty] | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [19 empty] | ? | ? | ? | ? | M | ? | M | FY16/T? | [14 empty] | 2017.08.31 |  |  |  | Action: Reviewing Store Point solution so MHSTP can reuse it and have updated mid March (CHRISTER) Agree follow up structure with Eva until meeting beginning of March (EvaLotta) Clarify if project or initative until meeting beginning of March ( EvaLotta)
NTV50 | Returns Prestudy | Running | FY15-T2 | 2015.01.01 | FY16-T1 | 2015.12.31 | Pre-Study | MHS TP | MHS Transformation Program | Return Management | [5 empty] | Convert visitors to happy customers so they return again | Marina Dubakina (acting) alt. Martin Hansson ( acting) |  | Retail & Expansions | Retail | [5 empty] | Fredrik Axen | Monica Holmvik-Persdotter | [18 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a | [37 empty] | Status: Will prestudy be ours? Need to follow up ownership | Status: New approach suggested and approved with Per Råborg and Monika Holmvik (through Rune Nylander) Actions: Identfiy cost and time to startup the initatives, during week 8 (STEFAN) Anchor new approach and release funds for Arhcitectural Investigation in MHSTP SG 10/3 (EVALOTTA) When approach approved update roadmap and MIH (Returns Prestudy > Architectural Investigation (EMIL)
NTV51 | Returns Project | Not Started | FY16-T2 | 2016.01.01 | FY18 - T3 | 2018.08.31 | Project | MHS TP | MHS Transformation Program | Return Management | Implement the recommended solution for cash and carry and return handling in store (not replacing SAMS). | Remove MHS return object and all functionality connected top the return flow. |  |  |  | Convert visitors to happy customers so they return again |  |  | Retail & Expansions | Retail | [10 empty] | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | n/a | [45 empty] | Action: Should it be renamed to Returns Managemen? (EMIL)
NTV52 | Business Credit Mgmt/RIMS | Running | FY15 T2 | 2015.01.01 | FY16 T2 | 2016.04.30 | Activity | MHS TP | MHS Transformation Program | Cash & Credit Mgmt | [8 empty] | Supporting | Same supporting | [69 empty] | Status: Need to sort out budget / Verify timeline & milestones / Start -up biweekly meetings Action: Meeting with Eva (BN & PM) | Status: Budget is sorted out for FY15 and FY16 Action: Update start - end date before next meeting (EMIL) Aling blueprint with Customer Finance Re-desing and secure re-plan for set-up of initative, in february (CHRISTER)
2167
|  | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1
77
4004
0.54121
Note on BC1: heand18: Prestudy has this information. Måste be projektledaren - Kan kolla med Emil först. Första uppskattningen ifrån förstudien.
Note on C2: hjoh: Not Started / Running / Closed
Note on H2: hjoh: Project / Pre-Study
Note on I2: hjoh: MHS TP Project / Dependency Project / Impacting Project
Note on L2: hjoh: Overall objective of the project.
Note on M2: hjoh: Objective from a MHS TP perspective
Note on O2: hjoh: MHS TP Objective Covered (Yes / no)
Note on P2: Link to MHS TP SG Meeting Minutes & Link to Roadmap Matrix ExcelbARA mhs tp
Note on AF2: heand18: YES - with comment
Note on AH2: heand18: YES/NO
Note on AJ2: hjoh: If it is a MHS TP governed and funded initiative, has it been arppoved by the SG?
Note on AK2: hjoh: Is the approach on how to deliver and the objective of the pre-study approved?
Note on AN2: Link draft PDI
Note on AR2: Link to SG Minutes
Note on AU2: heand18: Process forums and demand forums
Note on BA2: Information in Roadmap Matrix excel
Note on BC2: heand18: Bara MHS TP
Note on BF2: heand18: Have MHS TP been included in their dependency-mapping? For dependency and impacting projects to see if MHS TP is on the radar!
Note on BG2: heand18: P
Note on BH2: heand18: Organisation = People Samköra eventuella förändringar.
Note on BJ2: heand18: Technology
Note on BM2: heand18: Performance Levels & Output The introduction of new ways of working The phasing out of old ways of working Changes to existing ways of working
Note on BO2: heand18: New skill requirements from employees Cultural changes Staffing levels Employees moving from one role to another Training needs
Note on BR2: heand18: HIGH: Complex, many dependencies to other systems/integrations etc. MEDIUM: High effort, lower complexity LOW: Lower than above New computer systems Changes to existing technology systems Accomodation requirements - Procuring and selling buildings Machinery of heavy plant requirements Other equipment needs - Procuring or selling off equipment New network or too lsets
Note on BT2: heand18: • new reports • changes to existing reports or reporting systems • requirements for new data to feed into reports • project-specific data outcomes like occupancy rates if you were building a new hotel
Note on BY2: heand18: Also Current.
Note on CE2: heand18: Hur ska vi fånga progress mellan DP3 till DP8!
Note on BO3: heand18:
Note on Z4: heand18: Could not find MHS TP rep
Note on CB5: heand18: Planned date DP1: 2010-11-03
Note on CE5: heand18: Planned date D1: 2012-08-26
Note on CH5: heand18: Planned date DP1: 2014-01-01 PPO: 2015.06.15
Note on B6: heand18: csm & ship mgmt Information taken from LDI bimonthly.
Note on BY6: heand18: Plan at DP1 2014.02.07
Note on CB6: heand18: Plan at DP1: 31.01.2015
Note on CH6: heand18: Plan at DP3 2015.12.31 Plan at DP3:2016.08.31 Previous 2014.11.01: PPI:2015.12.30
Note on B8: heand18: Bara Frankrike och inte hela Centiro utrullningen.
Note on B9: heand18: Information taken from PPI - folder
Note on Z9: heand18: Could not find MHS TP rep
Note on BY9: heand18: Planned at DP1 2013.07.01
Note on CB9: heand18: PPI Planned at DP2: 2014.05.05 PTT: 2014.05.05
Note on CH9: heand18: Planned at DP3: 2016.08.31 Forecast: 2018.08.30
Note on B12: heand18: Closed? DWP Closed in PTT Tog DP3:an i slutet av januari.
Note on K12: heand18: Kommer kräva saker i de andra modulerna
Note on B13: heand18: FBIL
Note on CB13: heand18: Plan at DP1: 2013.12.15 PTT plan at DP1: 2013.12.20
Note on CH13: heand18: Planned at DP8: 2015.12.23 PPI planned at DP8: 2015.12.31
Note on B14: heand18: Case Mgmt
Note on B16: heand18: IFP
Note on H16: heand18: Förstudieaktigt - Förväntas bli ett program. Plan att bli program - d0-d1.
Note on H17: heand18: var ett program i grunden - var i grunden ett a. Ska startas om
Note on D18: heand18: FY 14
Note on B19: heand18: Sales Order Management Information taken from LDI bimonthly Kommer bli en del av eCommerce Går in i eCOM rollout
Note on F19: heand18: Plan at DP 3: 2016.08.19
Note on BY19: heand18: Planned at DP1: 2013.02.21
Note on CB19: heand18: Planned at DP1: 18.10.2013
Note on CE19: heand18: PTT Planned at DP1/3: 2015.05.05
Note on CH19: heand18: Plan at DP 3: 2016.08.19
Note on CN19: heand18: SOM är oro för varuhusordrar som aknske inte är i scope. Behöver vi lägga in ngt i vår plan. Multichannel Returns drivs av SOM. SOM lösning hanterar det ovh MCR kommer med kraven. Vi måste får reda på scopet av sales order management ecom - behöver vi isolera detta merr för att göra oss mindre beroende av dem? De har ett möte - EMIL har ett möte - 9.03.2015. Behöver nu veta kostadramar och hur detta påverkar vårt scope. Det behövs en extra insats. Vet ej hur mycket luft vi har i ramarna i range & supply - FY16 FY17? Stefa måste boxa den i tid och cost - EMIL snack med Christer. Stefan måste veta innan den 25.2.2015. Vi behöver bli mindre beroende - Behöver ge dem deadline för detta men har de detta i scopet. Måste finnas med i ramen innan den 25. Möte med CHRISTER.
Note on Z20: heand18: Could not find MHS TP rep
Note on BY20: heand18: Plan at DP1: 2014.01.22
Note on CB20: heand18: Plan at DP3: 2015.02.01 PTT Forecast: 2015.01.01
Note on CH20: heand18: Planned date at DP1: 2015.08.31
Note on B21: heand18: Hittar inte i PTT:n. Borde inte denna vara igång?
Note on B22: heand18: Information taken from PPI-folder Ingen information i PTT:n
Note on BY22: heand18: Planned date DP1: 2014-02-17
Note on CB22: heand18: Planned DP1:2014-08-26 Planned DP3:2015-05-28
Note on B23: heand18: Hittar ej i PTT:n Kommer bli en prestudy Work initiated - however not yet a formal prestudy.
Note on CJ23: heand18: We need for nD4
Note on CN23: heand18: Pågeamde diskussio9ner om detaljer i scope och förväntingar. Vi har iinebär av vissa förmågor. Vi måste veta vad som händer annars applikationsplatform. Äger applikationsplatform om vi skaffar den. Supportera oss. EMIL har möte på torsdag. Det finns planerade möten.
Note on B25: heand18: Prestudy between receipt mgmt and close cash mgmt Replace iPOS
Note on B26: heand18: Prestudy between receipt mgmt and close cash mgmt Replace iPOS
Note on B29: heand18: Kommer kanske köras tillsammans med Cash recon.-prestudy
Note on B30: heand18: Part of the critical line
Note on CN31: heand18: Inväntar Eva-Lotta. Vet ännu inte datum för denna. IT kan börja och göra den tekniska analysen. Ungefär som vi gör med returns - var sätter vi gränserna för customer order management tekniskt och sffärsmässigt. Ta bort saker i MHS som finns i iSell - Det vi kommer hamna i vad går gränsen. Det behövs ingen business projektledare men en business analyst behövs. En teknisk och business PM. 80 % TEK och 20 % BUS. Påbörjad diaolg med Rikard - Vi har haft möte med Lasse Gunnarsson om att det ska ligga i Rikard Klassons område. Henrik börjar i den tekniska biten - En risk är att få tag i en PM. Vad vill vi använda våra resutser till. Scopet är att den ska bort. Kan kickas igång så snart som möjligt. Den är inte beroende - om den glider in i 17 så är det okej.
Note on B34: heand18: Is a part of Pricing Mgmt. Have instead of Pricing Mgmt pre study and same dates apply as the pre-study.
Note on CJ34: heand18: Our part needs to be delivered so we know that target will be reached FY16. Critical is
Note on CN34: heand18: Beorenden som håller på att utredas. Klara inom någon månad. Estimat på kostnad har getts.
Note on B38: heand18: Information taken from PDI-folder Need to define what dependency we have.
Note on BY38: heand18: Planned date at DP1: 2014.07.23
Note on CB38: heand18: Planned date at DP3: 2015.01.30 Forecast: 2015.03.01
Note on CC38: heand18: Forecast 11.14 - ppi 2015.03.01
Note on B40: heand18: Merge SLF ans SGF Prestudy
Note on CJ40: heand18: Needed for DP4
Note on CN40: heand18: Förseanad... Taisto kommer vecka 9 med en ny plan. Kan vara en kostnadsmässig förändring om det blir en stor förskjutning på tid. JDA och IBM har ej kommit överens.
Note on B44: heand18: PoC has become Standardize Prepare Code but has a milestone now Standardize and Prepare
Note on T44: heand18: Driver själva inom programmet - Är en process. Secure IT Solutions.
Note on T45: heand18: Driver själva inom programmet - Är en process. Secure IT Solutions.
Note on T46: heand18: Driver själva inom programmet - Är en process. Secure IT Solutions.
Note on BM46: heand18: THIS INITATIVE WILL HAPPEN CONTINOUSLY. SHOULD IT BE HERE AT ALL?
Note on B50: heand18: SäljGrupp - Måste för att rulla ut Centiro som är ett måste för eCom - Vi kopplar bort flöden från MHS gällande ordar iSELL 2 delar i aktiviteten
Note on B51: heand18: Tar bort MHS roll i def skattesatser
Note on T51: heand18: David Roaelands
Note on B52: heand18: Kopplad till Support ticket mgmt
Note on U52: heand18: Annelie
Note on B53: heand18: Stor föränding - Beroende mot Sales Order Management.
Note on T54: heand18: Business credit
Note on U54: heand18: Managed by: Herbert Huth

## Capabilities
https://service.projectplace.com/pp/pp.cgi/r1019663424

## Information
https://service.projectplace.com/pp/pp.cgi/r1018876369

## Information objects
Information objects | TAL2020 Mapping | Comment
Accounting Base Data | Finance
Activities | ??Market and Customer
Article descriptions | Complete Offer
Assembly item | Complete Offer
Bank deposits | Finance
Business units | ??Properties
Cash&Carry order | ??Complete Offer
Commercial Classfication | Complete Offer
Commercial effiency | Complete Offer
Commercial qty | Complete Offer
Credit card | Finance
Currency | Finance
Customer Identification Types | Market and Customer
customer order lead time | Complete Offer
Customer Order return (old) | ??Market and Customer
Delivered today | ??Supplier
Delivery priority | ??Supplier
Discounts | Complete Offer
Distribution order | ??Agreement
DWP | ??Complete Offer
End date sale | Complete Offer
End Of Sales Day | ??Finance
External storage types | ?? | categorization of storage of non ikea items such as office items, AS IS, appliances
Fire class | ??
Fixed decoration | Complete Offer
Forecast | ??Complete Offer
Forecast activity | ??Complete Offer
Forecast index over a year | ??Complete Offer
Forecast parameters | ??Complete Offer
Gross margin | Finance
HFB | Complete Offer
Home delivery parameters | Complete Offer
ID Article
Internal orders | ??
Internal replenishment orders | ??
Internal Replenishment parameters | ??
Internal transactions | ??
Inventory/Stock accuracy | ??
Item - supplier relation | ??Supplier
Item available in store | Complete Offer
Item classification | Complete Offer
Item free of freight | Complete Offer
Item pictures | Complete Offer
Item reservation
Item type | Complete Offer
item-store relation
Last date for delivery
Last week in stock
Lead time | Supplier
Limit for exceptional orders
Local price | Complete Offer
Media info | Complete Offer
Minimum delivery lead time
Minimum Delivery Quantity
No of visitors
Number of times with local shortage
Order parameters
Order point
Orders
Payment codes
Payment In Advance
Pick order
Prices | Complete Offer
Product Areas | Complete Offer
Product code | Complete Offer
Product dominance | Complete Offer
Purchase price | ??Finance
Quality Class | Complete Offer
Range group | Complete Offer
Range group performance
Receipt | Business Transaction
Received today
Replenishment level
Return order | Business Transaction
Return parameters | Business Transaction
Return reasons | Business Transaction
Return ticket | Business Transaction
Safety stock | Complete Offer
Sales activity
Sales data
Sales department
Sales dimensions
Sales divisions
Sales information
Sales location | Complete Offer
Sales location alert | Complete Offer
Sales location data | Complete Offer
Sales location parameters | Complete Offer
Sales method | Complete Offer
Sales notifications | Complete Offer
Sales order | ??Agreement
Sales start date | Complete Offer
Sales stop | Complete Offer
Sales TAX definitions | Finance
Service class
Service classes
Service Office Adress info | Property
Shortage
Shortage parameters
Size of all sales places | Complete Offer
Sold last week
Speciality shop
Stamp duty | Finance
Stock figures
Stock movements
Storage
Storage location
Storage locations
Storage parameters
Store Departments contact info | Property
Store type | Property
STORE_PAR
SU-Item relation
Supplier matrix | Supplier
TAX | Finance
Three aces & king | Complete Offer
Type of sales space | Complete Offer
Users | Co-worker
VAT rates | Finance
Work area

## Screens
Classic/Web | Screen | Name | Type | Action | Initiative | Functional area | Comment
Classic | A | Sales | Menu |  | Remove Customer Order Mgmt
Classic | A1 | MHS booking system | Write | Delete | Remove Customer Order Mgmt
Classic | A2 | Show articles/reservation | Read |  | SGF Project
Classic | A3 | Credit status | Read |  | Credit Management
Classic | A4 | Sales administration | Menu |  | Remove Customer Order Mgmt
Classic | A41 | Sales information, update | Write
Classic | A42 | Activities, update | Write | Used?
Classic | A43 | 4629 Activities, list | List | Migrate | Secure MHS Reporting | SGF
Classic | A45 | Texts, administration | Write | Delete | Cleanup
Classic | A46 | 4635 All local prices | List | Migrate | Secure MHS Reporting | Sales
Classic | A47 | 4688 Art. to be discontinued | List | Delete | Secure MHS Reporting
Classic | A4F | 5024 Sales steering tool | List | Migrate | Secure MHS Reporting | SLM
Classic | A4L | 4632 Activity follow-up | List | Migrate | Secure MHS Reporting | Sales follow up
Classic | A4M | Send article info to RIX | Batch |  | Integration
Classic | A4N | Fetch article info from RIX | Batch |  | Integration
Classic | A4O | Fetch lead times from RIX | Batch |  | Integration
Classic | A5 | Returns removal confirmation | Write |  | Support ticket Management
Classic | B | Customer service | Menu |  | Remove Customer Order Mgmt
Classic | B1 | MHS booking system | Write | Delete | Remove Customer Order Mgmt
Classic | B2 | Show articles/reservation | Read |  | SGF Project
Classic | B3 | Credit status | Read |  | Credit Management
Classic | B4 | Corr. of reserv. stock BU | Write |  | SGF Project
Classic | B5 | Show complete art. info | Read |  | SGF Project
Classic | B6 | Order lists | Menu | Delete | Secure MHS Reporting
Classic | B61 | 4646 Report, art./booking no. | List | Delete | Secure MHS Reporting
Classic | B62 | 4648 Report, bookings/art.no. | List | Delete | Secure MHS Reporting
Classic | B7 | Automatic runs | Menu
Classic | B71 | Auto article allocation | Batch
Classic | B72 | Orders ready for notification | Batch
Classic | B73 | 4650 Print notification cards | List | Delete | Secure MHS Reporting
Classic | B74 | 4651 Print self-serve notific | List | Delete | Secure MHS Reporting
Classic | B75 | 4682 Reserv. stock value & qty | List | Delete | Secure MHS Reporting
Classic | BB | 4696 Transport paper | List | Delete | Secure MHS Reporting
Classic | BC | Send VAT Specification to CIAR | Batch
Classic | BE | Returns lists | Menu
Classic | BE1 | 6530 Today's POS-proc. returns | List | Migrate | Secure MHS Reporting | Customer relation
Classic | BE2 | 6531 Security/mail cheque | List | Migrate | Secure MHS Reporting | Customer relation
Classic | BE3 | 6532 Customer accommodation | List | Migrate | Secure MHS Reporting | Customer relation
Classic | BE4 | 6534 Card refunds | List | tbd | Secure MHS Reporting | Customer relation
Classic | C | Goods administration | Menu
Classic | C1 | Article file maintenance | Menu
Classic | C11 | Enter complete article info | Write |  | Range management
Classic | C16 | Inv. signal, sales & res. stop | Write |  | SGF Project
Classic | C18 | Maintain sales space capacity | Write | Delete | Cleanup | No access
Classic | C1C | Lead time factor | Write | Delete | Cleanup | No access
Classic | C1E | Order new article number | Write | Delete | Cleanup | No access
Classic | C1F | Mark article for deletion | Write |  | Range management
Classic | C1G | Update local price | Write |  | Highest Local Price
Classic | C1H | Find article via name | Read | Delete | Remove Customer Order Mgmt
Classic | C1I | Show complete art. info | Read |  | SGF Project
Classic | C1K | Temporary Family marking | Write |  | Highest Local Price
Classic | C1M | 4613 Central article updates | List | Migrate | Secure MHS Reporting | Range admin
Classic | C1N | 4683 New articles | List | Migrate | Secure MHS Reporting | Range admin
Classic | C1O | 6030 Arts. possible to delete | List | tbd | Secure MHS Reporting | Range admin
Classic | C2 | Ordering | Menu
Classic | C21 | Process order proposal | Write | Delete | SGF Project
Classic | C22 | 4608 Order proposal | List | Delete | Secure MHS Reporting
Classic | C23 | Manual orders | Write |  | SGF Project
Classic | C24 | 4603 Today's orders | List | Delete | Secure MHS Reporting
Classic | C26 | Available in delivery plan | Read | Delete | SGF Project | No access
Classic | C27 | Orders per article | Read |  | SGF Project
Classic | C28 | 4605 Stock replenishment | List | Migrate | Secure MHS Reporting | SRS
Classic | C29 | 4601 All arts. with SRP = 2&3 | List | Delete | Secure MHS Reporting
Classic | C2A | 4607 Errors, requirement calc. | List | Delete | Secure MHS Reporting
Classic | C2B | 5600 Order changes received | List | Delete | Secure MHS Reporting
Classic | C3 | Inventory | Menu
Classic | C31 | 4618 Inventory list | List | Migrate | Secure MHS Reporting | SGF
Classic | C34 | 4620 Last inventory/article | List | Migrate | Secure MHS Reporting | SGF
Classic | C35 | Order inventory | Write | Delete | Cleanup | No access
Classic | C36 | Entry of inventory counts | Write | Delete | Cleanup | No access
Classic | C37 | 4621 Inventory checklist | List | Migrate | Secure MHS Reporting | SGF
Classic | C38 | 4622 Result - all articles | List | Delete | Secure MHS Reporting
Classic | C39 | 4623 Result - differences only | List | Delete | Secure MHS Reporting
Classic | C3A | 4691 Create inventory trans. | List | Migrate | Secure MHS Reporting | SGF
Classic | C3B | Delete inventory | Write | Delete | Cleanup | No access
Classic | C3C | Inventories not yet updated | Write | Delete | Cleanup | No access
Classic | C3D | 4624 Spot inventory | List | Migrate | Secure MHS Reporting | SGF
Classic | C4 | Deliveries and stock transfers | Menu
Classic | C42 | Create carrier register | Batch
Classic | C43 | Receiving report (AR2) TT200 | Write |  | SGF Project
Classic | C44 | Find auto. direct deliveries | Write |  | SGF Project
Classic | C45 | Auto. direct deliveries TT210 | Write |  | SGF Project
Classic | C46 | Manual direct deliveries TT210 | Write |  | SGF Project
Classic | C47 | Corr. of dir. deliveries TT211 | Write |  | SGF Project
Classic | C48 | Inter store - incoming TT220 | Write |  | SGF Project
Classic | C49 | Dispatch to supplier TT250 | Write |  | SGF Project
Classic | C4A | Inter store - outgoing TT260 | Write |  | SGF Project
Classic | C4B | Display transfers TT310 | Write |  | SGF Project
Classic | C4C | Office transfers TT315 | Write |  | SGF Project
Classic | C4D | Returns TT320-325 | Write |  | SGF Project
Classic | C4E | Quality claims TT330 | Write |  | SGF Project
Classic | C4F | Intern./Rec. damages TT390-391 | Write |  | SGF Project
Classic | C4G | Stock adjustment TT440-441 | Write |  | SGF Project
Classic | C4H | Recovery - back to stock TT450 | Write |  | SGF Project
Classic | C4I | IKEA At Work TT470-471-472 | Write |  | Credit management
Classic | C4J | IKEA Charge A/C TT490-491 | Write |  | Credit management
Classic | C4K | IKEA Loan TT480-481 | Write | Delete | Credit management
Classic | C4L | 4616 Delivery note status | List | Migrate | Secure MHS Reporting | SGF
Classic | C4M | 4604 New delivery notes (AR1) | List | Migrate | Secure MHS Reporting | SGF
Classic | C4N | 4617 Incoming delivery signal | List | Migrate | Secure MHS Reporting | SGF
Classic | C4O | Recovery - Damage follow up | Write |  | Support ticket Management
Classic | C6 | Working & control reports | Menu |  | n/a
Classic | C61 | 4600 Range list | List | Delete | Secure MHS Reporting
Classic | C62 | 4680 Self-serve picking list | List | Delete | Secure MHS Reporting
Classic | C63 | 4625 Low-level articles | List | Migrate | Secure MHS Reporting | SRS
Classic | C64 | 4609 Today's internal trans. | List | Migrate | Secure MHS Reporting | SGF
Classic | C65 | 4630 Today's IKEA Contr. trans | List | Migrate | Secure MHS Reporting | Cash Office Admin
Classic | C66 | 4663 Self-serve reservations | List | Delete | Secure MHS Reporting
Classic | C69 | 4637 Local shortage articles | List | Delete | Secure MHS Reporting
Classic | C6B | Send weekly stock info to SOS | Batch | Used? | Integration
Classic | C6C | 4400 Flexible stock | List | Delete | Secure MHS Reporting
Classic | C6D | 4401 Flexible stock, detailed | List | Migrate | Secure MHS Reporting | SRS
Classic | C7 | Statistic reports | Menu | Delete | Secure MHS Reporting
Classic | C71 | 5301 Daily statistics | List | Migrate | Secure MHS Reporting | Sales follow up
Classic | C72 | 5302 Weekly statistics | List | Migrate | Secure MHS Reporting | Sales follow up
Classic | C73 | 5303 Weekly statistics,Contr. | List | Migrate | Secure MHS Reporting | Sales follow up
Classic | C74 | 5316 Weekly statistics,Bargain | List | Migrate | Secure MHS Reporting | Sales follow up
Classic | C75 | 4664 Top 50 | List | Migrate | Secure MHS Reporting | Sales follow up
Classic | C76 | 4690 Sales statistics,Family | List | Migrate | Secure MHS Reporting | Sales follow up
Classic | C77 | 5305 Overstock & concrete arts | List | Delete | Secure MHS Reporting
Classic | C78 | 5304 Weekly stat., int. trans. | List | Migrate | Secure MHS Reporting | Sales follow up
Classic | C79 | 6700 Article movements | List | Migrate | Secure MHS Reporting | SGF
Classic | C7A | 6701 Art. movements, summary | List | Migrate | Secure MHS Reporting | SGF
Classic | C7B | 5306 Recovery index | List | Delete | Secure MHS Reporting
Classic | C7C | 6001 Service level, statistics | List | tbd | Secure MHS Reporting | SRS
Classic | C7D | 6002 Service level, articles | List | tbd | Secure MHS Reporting | SRS
Classic | C7E | 6003 Upcoming shortages | List | tbd | Secure MHS Reporting | SRS
Classic | C8 | List spooler | Write | Delete | Secure MHS Reporting
Classic | D | System | Menu
Classic | D1 | System administration | Menu
Classic | D11 | Add users | Write | Migrate | Standardization
Classic | D12 | Change password | Write | Migrate | Standardization
Classic | D13 | 2222 Report - all users | List | Delete | Secure MHS Reporting
Classic | D14 | Store parameters | Write | Migrate | Standardization
Classic | D16 | Form texts & reservation time | Write | Delete | Remove Customer Order Mgmt
Classic | D17 | Control values | Write | Migrate | Standardization
Classic | D18 | Currency parameters | Write | Migrate | Standardization
Classic | D1A | 4685 Staff purchases | List | Migrate | Secure MHS Reporting | HR
Classic | D1B | Clear staff purchases | Batch |  |  | HR
Classic | D1C | Maintain department | Write | Migrate | Standardization
Classic | D1D | 4686 Staff purch./yr/employee | List | Migrate | Secure MHS Reporting | HR
Classic | D1F | Receive staff purchase info | Batch | Used? | Integration
Classic | D1G | Maintain BS access rights | Write | Delete | Cleanup
Classic | D2 | System operations | Menu
Classic | D21 | Immediate batch | Write | Migrate | Standardization
Classic | D22 | Morning batch | Write | Migrate | Standardization
Classic | D23 | Evening batch | Write | Migrate | Standardization
Classic | D24 | Weekly batch | Write | Migrate | Standardization
Classic | D25 | End of year batch | Write | Migrate | Standardization
Classic | D26 | Special batch 6 | Write | Migrate | Standardization
Classic | D27 | Special batch 7 | Write | Migrate | Standardization
Classic | D28 | Special batch 8 | Write | Migrate | Standardization
Classic | D29 | Special batch 9 | Write | Migrate | Standardization
Classic | D2C | Stop user | Write | Used? | Cleanup
Classic | D2E | Windows printer setup | Write | Migrate | Standardization
Classic | D2I | Recreate Spool & Trans.files | Write | Used? | Cleanup
Classic | D2K | Batch analysis | Read | Used? | Cleanup
Classic | D3 | BOS Batch I | Menu
Classic | D31 | Returns-Update curr low prices | Batch
Classic | D32 | Update local prices | Batch
Classic | D33 | Clear stock movements | Batch
Classic | D34 | Returns-Erase old transactions | Batch
Classic | D35 | Create AR2 (TT200) file | Batch
Classic | D36 | Create AR2 (TT210/211) file | Batch
Classic | D37 | Requirement calculation | Batch
Classic | D38 | Update base-on-hand | Batch
Classic | D39 | Report & reset weekly fields | Batch
Classic | D3A | Load new internal AR1 | Batch | Delete | No access
Classic | D3C | Update article classification | Batch | Delete | No access
Classic | D3D | Set initial stock date/qty | Batch
Classic | D3E | Start daily backup | Batch
Classic | D3F | Send shortage info to SOS | Batch | Used?
Classic | D3G | Load global section | Batch
Classic | D3H | Run command procedures | Batch
Classic | D3I | Delete old param files | Batch
Classic | D3J | Article info to central | Batch
Classic | D3K | Price change - NEW CATALOGUE | Batch
Classic | D3L | Update/delete new articles | Batch
Classic | D3M | Update delivery times | Batch
Classic | D3N | Today's date | Batch
Classic | D3O | Update order register | Batch
Classic | D3P | Update sales group & cust.stat | Batch
Classic | D3Q | Update internal trans. stats. | Batch
Classic | D3R | Update stock statistics | Batch
Classic | D3S | Week history batch | Batch
Classic | D3T | Year history batch | Batch
Classic | D3U | Send shortage type to central | Batch
Classic | D4 | BOS Batch II | Menu
Classic | D41 | Prep. before PTAG's morn.batch | Batch
Classic | D42 | Update supplier information | Batch
Classic | D45 | Service level to Cockpit | Batch
Classic | D48 | Send IAW to IKANO | Batch
Classic | D49 | Receive activities SOS | Batch | Used?
Classic | D4A | Receive article changes | Batch
Classic | D4E | Send daily sales, stock to SOS | Batch | Used?
Classic | D4F | Send internal trans to SOS | Batch | Used?
Classic | D4H | Changes in article file to SOS | Batch | Used?
Classic | D4L | Create invoice trans.order | Batch
Classic | D4M | Send average sales | Batch
Classic | D4N | Delete internal transactions | Batch
Classic | D4O | Create invoice transaction | Batch
Classic | D4R | Transfer trans. centr. system | Batch
Classic | D4T | Pay in advance to RIMS | Batch
Classic | D4U | Send IKEA At Work to RIMS | Batch
Classic | D4V | Account/loan from tills | Batch
Classic | D5 | POS Batch | Menu
Classic | D52 | Stop selling in POS system | Batch
Classic | D53 | Update BOS from POS journal | Batch
Classic | D54 | Send cashier info to POS | Batch
Classic | D55 | Load total PLU in POS | Batch
Classic | D56 | Reset POS journal to zero | Batch
Classic | D58 | Create trans. Family reward | Batch
Classic | D5A | Stop list DK | Batch
Classic | D5B | Foreign currency report | Batch
Classic | D5C | Update sales grp from POS | Batch
Classic | D5D | Update whitelist IPJ | Batch
Classic | D5G | Clear daily stat sales group | Batch
Classic | D5H | Update whitelist Account | Batch
Classic | D5I | Maintain POS events | Batch
Classic | D5J | Update card information | Batch
Classic | D5K | Update credit information | Batch
Classic | D5M | Send articles to PQS | Batch
Classic | D5N | Send POS/Return info to MDB | Batch
Classic | D5O | Update cash statistics | Batch
Classic | D6 | BOS Batch III | Menu
Classic | D61 | Send VMI Sales & Stock info | Batch
Classic | D62 | Create analysis data | Batch
Classic | D63 | Send analysis data to IKEA DW | Batch
Classic | D65 | Create analysis data | Batch
Classic | D66 | Send goods availability to SOS | Batch
Classic | D68 | Delivery information to OMS | Batch
Classic | D6B | Stock & local price to NIVA | Batch
Classic | D6C | Erase old DWP data | Batch
Classic | D6D | Concrete,overstock,sale/IBIS | Batch
Classic | D6E | Cleanup CPS Orders | Batch
Classic | D7 | BOS BATCH IV | Menu
Classic | D71 | Receive article info RIX | Batch
Classic | D72 | Receive Availability Info | Batch
Classic | D7A | Receive Safety Stock RIX | Batch
Classic | D7B | Consolidated forecast | Batch
Classic | D7C | Receive Sales Day Index RIX | Batch
Classic | D7D | Receive SRS flow params RIX | Batch
Classic | D7F | Receive Average Forecast RIX | Batch
Classic | D7R | Receive Rollout Control RIX | Batch
Classic | D8 | BOS Batch V | Menu
Classic | D82 | SLM Art Info To Central | Batch
Classic | D84 | SLM info to IDW | Batch
Classic | D85 | SLM KPI data to IDW | Batch
Classic | D86 | SLM Info to RIX | Batch
Classic | D8A | Activate Sales loc. changes | Batch
Classic | D8B | SLM Move | Batch
Classic | D8C | SSQ Calculations | Batch
Classic | D8D | Clean up SLM tables | Batch
Classic | D8E | Other SLM calculations | Batch
Classic | D8F | Central Forecast Emulator | Batch
Classic | E | Cash administration | Menu
Classic | E1 | Registration | Menu
Classic | E11 | Withdraw float | Write | Delete | Cash Office Mgmt cleanup
Classic | E12 | Inpayments cash register | Write | Delete | Cash Office Mgmt cleanup
Classic | E13 | Cheques III | Write | Delete | Cash Office Mgmt cleanup
Classic | E14 | 4662 Cash reconciliation | List | Delete | Secure MHS Reporting
Classic | E15 | Inpayment-bank | Write | Delete | Cash Office Mgmt cleanup
Classic | E16 | Foreign currency accounting | Write | Delete | Cash Office Mgmt cleanup
Classic | E17 | Inpayment receipt | Write | Delete | Cash Office Mgmt cleanup
Classic | E18 | Outpayment receipt | Write | Delete | Cash Office Mgmt cleanup
Classic | E19 | Inpayment-bank plus/minus | Write | Delete | Cash Office Mgmt cleanup
Classic | E1A | Number of visitors | Write | Delete | Cash Office Mgmt cleanup
Classic | E1B | Cashier authority | Write | Delete | Cash Office Mgmt cleanup
Classic | E1D | Clear number of visitors | Batch
Classic | E1E | Clear daily sales & VAT | Batch
Classic | E1F | Sales adjustment TT431 +/- | Write | ? | ?
Classic | E2 | Lists / statistics | Menu
Classic | E21 | 4670 Cashier rep. cashier/day | List | Migrate | Secure MHS Reporting | Cash Office Admin
Classic | E22 | 4677 Cash diff. stated day | List | Delete | Secure MHS Reporting
Classic | E23 | 4676 Withdraw float stated day | List | Delete | Secure MHS Reporting
Classic | E24 | 4669 Statistics POS | List | Migrate | Secure MHS Reporting | Cash Office Admin
Classic | E25 | 4705 Receipts list | List | Delete | Secure MHS Reporting
Classic | E26 | 4674 Cust./half hr/checkout | List | Delete | Secure MHS Reporting
Classic | E27 | 4675 Items/half hr/checkout | List | Delete | Secure MHS Reporting
Classic | E28 | 4706 Cust./half hr/full serve | List | Migrate | Secure MHS Reporting | HR
Classic | E29 | 4707 Cash statistics | List | Delete | Secure MHS Reporting
Classic | E2A | 4701 Sales grp. tot/date/cash. | List | Migrate | Secure MHS Reporting | Cash Office Admin
Classic | E2B | 4702 Sales group cashier | List | Migrate | Secure MHS Reporting | Cash Office Admin
Classic | E2C | 4703 Sales group total/cashier | List | Migrate | Secure MHS Reporting | Cash Office Admin
Classic | E2D | 4704 Sales groups total | List | Migrate | Secure MHS Reporting | Cash Office Admin
Classic | E2E | 4678 Cash diff./cashier | List | Delete | Secure MHS Reporting
Classic | E2F | 4667 Cash diff. store all cash | List | Delete | Secure MHS Reporting
Classic | E2G | 4673 Canc./keying error stat. | List | Delete | Secure MHS Reporting
Classic | E2K | 4684 VAT account | List | Delete | Secure MHS Reporting
Classic | E2L | 4679 VAT report France | List | Delete | Secure MHS Reporting
Classic | E2M | 4697 Control report VAT-rate | List | Delete | Secure MHS Reporting
Classic | E2N | 4698 Stamp Duty monthly report | List | Delete | Secure MHS Reporting
Classic | E2O | 4711 COL with det. VAT specs | List | Delete | Secure MHS Reporting
Classic | E2P | 4712 VAT per return trans, det | List | Delete | Secure MHS Reporting
Classic | E2Q | Send full serve statistics | Batch
Classic | E3 | Business Unit Accounting | Menu
Classic | E31 | 4708 Business accounting-perm. | List | Delete | Secure MHS Reporting
Classic | E32 | Listlayout business accounting | Write | Delete | Cash Office Mgmt cleanup
Classic | E33 | Sales restaur., others not MHS | Write | Delete | Cash Office Mgmt cleanup
Classic | E34 | Daily sales | Batch
Classic | E36 | 4709 Late DDS/RDU information | List | Delete | Secure MHS Reporting
Classic | F | SO Menu | Menu
Classic | F2 | Maint. of GLO_SPOOL$PRINTER | Write | Delete | Secure MHS Reporting
Classic | F4 | 1111 All texts | List | Delete | Secure MHS Reporting
Classic | F5 | 3333 All menus | List | Delete | Secure MHS Reporting
Classic | F6 | Parameter maintenance | Write | Migrate | Standardization
Classic | F7 | Delete old cash reconc's | Batch
Classic | F8 | Modifies mail consumer table | Write | Used? | Cleanup
Classic | F9 | Currency parameters | Write | Delete | Cash Office Mgmt cleanup
Classic | FA | SO parameters | Write | Migrate | Standardization
Classic | FB | VAT rates | Write | Delete | Tax info & calculation
Classic | FC | Discount parameters | Write | Delete | Pricing mgmt
Classic | FD | Pay codes | Write | Delete | Cash Office Mgmt cleanup
Classic | FN | Maintenance consignmentnote no | Write | Used? | Cleanup | SGF
Classic | FO | Card parameters/identification | Write | Delete | Cash Office Mgmt cleanup
Classic | H | SRS | Menu
Classic | H1 | Maintain SRS parameters | Write |  | One Common Replenishment | SRS
Classic | H2 | Maintain promotions | Write |  | One Common Replenishment | SRS
Classic | H3 | Maintain week indices | Write |  | One Common Replenishment | SRS
Classic | H4 | Maintain sales jumps, article | Write |  | One Common Replenishment | SRS
Classic | H5 | Maintain sales jumps, range | Write |  | One Common Replenishment | SRS
Classic | H6 | Show article information | Read |  | One Common Replenishment | SRS
Classic | H7 | Maintain article information | Write |  | One Common Replenishment | SRS
Classic | H8 | Maintain lead time variability | Write |  | One Common Replenishment | SRS
Classic | H9 | Initiate/delete article | Write |  | One Common Replenishment | SRS
Classic | HA | Sales Space Management | Menu
Classic | HA1 | Maintain SSM parameter | Write |  | One Common Replenishment | SRS
Classic | HA2 | SSM article information | Read | Delete | No access | SRS
Classic | HB | Maintain day indices | Write |  | One Common Replenishment | SRS
Classic | HC | Maintain short detection level | Write |  | One Common Replenishment | SRS
Classic | HD | SRS batches | Menu
Classic | HD1 | Get MHS daily information | Batch
Classic | HD2 | Get reservation comp | Batch
Classic | HD3 | Calculate shortage comp | Batch
Classic | HD4 | Get MHS weekly information | Batch
Classic | HD5 | Calculate sales forecast & SSF | Batch
Classic | HD6 | Update MHS | Batch
Classic | HD7 | SRS yearly batch | Batch
Classic | HD8 | Calculate delivery type | Batch
Classic | HD9 | Send MHS key figures to SOS | Batch
Classic | HDA | Calculate SRS flow parameters | Batch
Classic | HDB | SRS data to Central | Batch
Classic | HE | SRS reports | Menu
Classic | HE1 | 6800 New articles | List | Migrate | Secure MHS Reporting | Range admin
Classic | HE2 | 6801 No mhs upd/hist frozen | List | Migrate | Secure MHS Reporting | SRS
Classic | HE3 | 6802 Gds dom & Auto bin effect | List | Delete | Secure MHS Reporting
Classic | HE4 | 6803 Articles with promotions | List | Migrate | Secure MHS Reporting | SRS
Classic | HE5 | 6804 Articles with sales jumps | List | Migrate | Secure MHS Reporting | SRS
Classic | HE6 | 6805 Critical forecast errors | List | Migrate | Secure MHS Reporting | SRS
Classic | HE7 | 6806 Weekly summary | List | Migrate | Secure MHS Reporting | SRS | rw010
Classic | HE8 | 6807 Check stock balance | List | Migrate | Secure MHS Reporting | SRS
Classic | HE9 | 6808 Sugg., sales space capac. | List | tbd | Secure MHS Reporting | SRS
Classic | HEA | 6809 Maintain salesspace, summ | List | Delete | Secure MHS Reporting
Classic | J | CIS | Menu
Classic | J1 | MHS booking system | Write |  | Remove Customer Order Mgmt
Classic | J2 | Show articles/reservation | Read |  | SGF Project
Classic | J3 | Credit status | Read |  | Credit management
Classic | J4 | Corr. of reserv. stock BU | Write |  | SGF Project
Classic | J5 | Show complete art. info | Read |  | SGF Project
Classic | J6 | Reg. message on deliv. order | Write |  | Remove Customer Order Mgmt
Classic | J8 | Lists Own stock | Menu
Classic | J81 | 4646 Report, art./booking no. | List | Delete | Secure MHS Reporting
Classic | J82 | 4648 Report, bookings/art.no. | List | Delete | Secure MHS Reporting
Classic | J83 | 4650 Print notification cards | List | Delete | Secure MHS Reporting
Classic | J84 | 4651 Print self-serve notific | List | Delete | Secure MHS Reporting
Classic | J85 | 4682 Reserv. stock value & qty | List | Delete | Secure MHS Reporting
Classic | J86 | 4695 VAT Specification | List | Delete | Secure MHS Reporting
Classic | J87 | 4696 Transport paper | List | Delete | Secure MHS Reporting
Classic | J88 | 7013 Quotations to expire | List | Delete | Secure MHS Reporting
Classic | J89 | 7016 Deleted C&C & Draft ords | List | Delete | Secure MHS Reporting
Classic | J8A | 7030 Mon existing Draft orders | List | Delete | Secure MHS Reporting
Classic | J9 | Batches COS | Menu
Classic | J91 | Receive lead time trans fr COS | Batch | Delete
Classic | J92 | Receive local holiday (COS) | Batch | Delete
Classic | J93 | Rec. day convers. fac. fr. COS | Batch | Delete
Classic | J94 | Receive new & chg orders (COS) | Batch | Delete
Classic | J95 | Delete logs of changes | Batch | Delete
Classic | J96 | Send PIA to COS | Batch | Delete
Classic | J97 | Ret./Repl. order conf. to COS | Batch | Delete
Classic | J98 | Receive zip/area codes fr. COS | Batch | Delete
Classic | J99 | Receive trans 5025 <=COS | Batch | Delete
Classic | J9A | Rec. Ret./Repl. trans. fr. COS | Batch | Delete
Classic | J9B | Send AR2 to COS | Batch | Delete
Classic | J9C | Receive freight costs (COS) | Batch | Delete
Classic | JA | Batches SOS | Menu
Classic | JA2 | Receive PA updates | Batch | Delete
Classic | JA3 | Receive PRA updates | Batch | Delete
Classic | JB | Other batches | Menu
Classic | JB1 | Upd./release art. reservations | Batch
Classic | JB2 | Auto article allocation | Batch
Classic | JB3 | Orders ready for notification | Batch
Classic | JB4 | Receive Remote Stock List Info | Batch
Classic | JB5 | Send Kitchen Draft to LCOFF | Batch
Classic | JC | Lists Distribution orders | Menu
Classic | JC1 | 7002 Problem ords/7001 Letters | List | Delete | Secure MHS Reporting
Classic | JC2 | 7003 Rejected orders | List | Delete | Secure MHS Reporting
Classic | JC3 | 7004 Mon failed credit checks | List | Delete | Secure MHS Reporting
Classic | JC4 | 7005 Mon changed freight costs | List | Delete | Secure MHS Reporting
Classic | JC5 | 7006 Monitor changed prices | List | Delete | Secure MHS Reporting
Classic | JC6 | 7007 Monitor discounts | List | Delete | Secure MHS Reporting
Classic | JC7 | 7008 Distr. orders with PIA, | List | Delete | Secure MHS Reporting
Classic | JC8 | 7009 Unpaid/Paid too much PIA | List | Delete | Secure MHS Reporting
Classic | JC9 | 7010 Order stats by mode | List | Delete | Secure MHS Reporting
Classic | JCA | 7011 Delivered orders | List | Delete | Secure MHS Reporting
Classic | JCB | 7012 Placed orders last week | List | Delete | Secure MHS Reporting
Classic | JCC | 7014 Blocked orders | List | Delete | Secure MHS Reporting
Classic | JCD | 7015 Delivered, not invoiced | List | Delete | Secure MHS Reporting
Classic | JCE | 7017 Overruled credit limits | List | Delete | Secure MHS Reporting
Classic | JCF | 7018 Conf. Distr. return ords | List | Delete | Secure MHS Reporting
Classic | JCG | 7019 Deleted Distrib. orders | List | Delete | Secure MHS Reporting
Classic | JCH | 7020 Monitor exceptional ords | List | Delete | Secure MHS Reporting
Classic | JCI | 7021 Replied exceptional ords | List | Delete | Secure MHS Reporting
Classic | JCJ | 7022 Print customer notific | List | Delete | Secure MHS Reporting
Classic | JCK | 7023 Cancelled Distr. orders | List | Delete | Secure MHS Reporting
Classic | JCL | 7024 Complete PIA | List | Delete | Secure MHS Reporting
Classic | JCM | 7026 PIA payments | List | Delete | Secure MHS Reporting
Classic | JCN | 7031 Mon chg value on add serv | List | Delete | Secure MHS Reporting
Classic | JCO | 7032 Sales per user ID | List | Delete | Secure MHS Reporting
Classic | JCP | 7033 Delivery (-ies) to cust. | List | Delete | Secure MHS Reporting
Classic | JD | Define freight charges | Write |  | Remove Customer Order Mgmt
Classic | JD1 | Fr. table cust. type/del. meth | Write |  | Remove Customer Order Mgmt
Classic | JD2 | Fr. table perc. of amount/zone | Write |  | Remove Customer Order Mgmt
Classic | JD3 | Fr. table weight interv./zone | Write |  | Remove Customer Order Mgmt
Classic | K | Security | Menu |  | Support ticket Management
Classic | K1 | Returns security investigation | Menu |  | Support ticket Management
Classic | K11 | Maintenance - ID 6533 | Write | Used? | Cleanup
Classic | K12 | Security investigation | Write |  | Support ticket Management
Classic | K13 | Inventory adjustment/audit | Write |  | SGF Project
Classic | K14 | Keying error adjustment | Write |  | Cash Office Mgmt cleanup
Classic | K15 | 6533 Security information | List | Delete | Secure MHS Reporting
Classic | K16 | 6535 Returns removals/adjustm. | List | Migrate | Secure MHS Reporting | Customer relation
Classic | K2 | Returns code maintenance | Menu |  | Support ticket Management
Classic | K21 | Valid ID types | Write |  | Support ticket Management
Classic | K22 | Manager approval code | Write |  | Support ticket Management
Classic | L | Store Goods Flow | Menu |  | SGF Project
Classic | L1 | Storage location admin. | Menu |  | SGF Project
Classic | L11 | Maintain storage locations | Write |  | SGF Project
Classic | L12 | Bar storage locations | Write |  | SGF Project
Classic | L13 | Maint.local pallet dimens&qtys | Write |  | SGF Project
Classic | L14 | Define allocation priorities | Write |  | SGF Project
Classic | L16 | Man. stock-out, normal arts. | Write |  | SGF Project
Classic | L18 | Man.stock-in/-out, extern.arts | Write |  | SGF Project
Classic | L19 | Man.stock-in/-out, sales group | Write |  | SGF Project
Classic | L1A | Define storage loc. size class | Write |  | SGF Project
Classic | L1B | Maintain ext.art.type desc | Write |  | SGF Project
Classic | L1C | Man.stock in/out, blackbox loc | Write |  | SGF Project
Classic | L1E | Article information | Read |  | SGF Project
Classic | L1F | Location information | Read |  | SGF Project
Classic | L2 | Internal ordering | Menu |  | SGF Project
Classic | L21 | Release AR-1, print pall.label | Write |  | SGF Project
Classic | L22 | Mark man'l intern.ords on AR-1 | Write |  | SGF Project
Classic | L23 | Preventative internal orders | Write |  | SGF Project
Classic | L25 | Intern. ords. for sales groups | Write |  | SGF Project
Classic | L28 | Maintain Work Area Description | Write |  | SGF Project
Classic | L2A | Print blind IPI labels | Print |  | SGF Project
Classic | L3 | All SGF lists | Menu |  | SGF Project
Classic | L31 | 8101 Stock movements log | List | tbd | Secure MHS Reporting | SGF
Classic | L32 | 8102 Graph. warehouse struc. | List | tbd | Secure MHS Reporting | SGF
Classic | L33 | 8103 Empty storage locations | List | tbd | Secure MHS Reporting | SGF
Classic | L34 | 8104 Occupied storage locat'ns | List | tbd | Secure MHS Reporting | SGF
Classic | L35 | 8105 Usage types/barring codes | List | tbd | Secure MHS Reporting | SGF
Classic | L36 | 8106 Stored external arts. | List | tbd | Secure MHS Reporting | SGF
Classic | L38 | 8108 Stored sales group arts | List | tbd | Secure MHS Reporting | SGF
Classic | L39 | 8111 Local pallet dimensions | List | tbd | Secure MHS Reporting | SGF
Classic | L3A | 8122 Internal order statistics | List | tbd | Secure MHS Reporting | SGF
Classic | L3B | 8123 OPEN internal orders | List | tbd | Secure MHS Reporting | SGF
Classic | L3C | 8124 Picking list | List | tbd | Secure MHS Reporting | SGF
Classic | L3D | 8131 Arts. in wrong SM area | List | tbd | Secure MHS Reporting | SGF
Classic | L3E | 8133 Capac. optim.-IntOrd prop | List | tbd | Secure MHS Reporting | SGF
Classic | L3F | 8134 Intern.ord'g using list | List | tbd | Secure MHS Reporting | SGF
Classic | L3G | 8136 Utilisat'n struct., summ | List | tbd | Secure MHS Reporting | SGF
Classic | L3H | 8137 Age structure | List | tbd | Secure MHS Reporting | SGF
Classic | L3I | 8138 Frequency - stock-in/-out | List | tbd | Secure MHS Reporting | SGF
Classic | L3J | 8140 Filling rate list | List | tbd | Secure MHS Reporting | SGF
Classic | L3K | 8151 Optim. cap., merge stock | List | tbd | Secure MHS Reporting | SGF
Classic | L3L | 8152 SM0 art. in wrong HFB loc | List | tbd | Secure MHS Reporting | SGF
Classic | L4 | SGF batches | Menu |  | SGF Project
Classic | L41 | Del. old internal orders | Batch |  | SGF Project
Classic | L42 | Create frequency values | Batch |  | SGF Project
Classic | L43 | Delete old log entries | Batch |  | SGF Project
Classic | L44 | Delete statistics | Batch |  | SGF Project
Classic | L45 | Generate internal ord. stats | Batch |  | SGF Project
Classic | L47 | Prepare data for spot inv. | Batch |  | SGF Project
Classic | L48 | SILO Storage Correction - 8110 | Batch |  | SGF Project
Classic | L49 | Calculate Indiv. Replen. Level | Batch |  | SGF Project
Classic | L5 | SGF Management | Menu |  | SGF Project
Classic | L51 | Workload overview | Read |  | SGF Project
Classic | L52 | Maintain unconfirmed stock ins | Write |  | SGF Project
Classic | L53 | View and confirm internal ord | Write |  | SGF Project
Classic | L54 | Order pre-notification calc | Write |  | SGF Project
Classic | L55 | Maintain Article Put Away Rule | Write |  | SGF Project
Classic | L56 | Define facility priorities | Write |  | SGF Project
Classic | L57 | Release Parking Area | Write |  | SGF Project
Classic | L58 | Adjust SGF movement parameters | Write |  | SGF Project
Classic | M | Inventory | Menu |  | SGF Project
Classic | M1 | Main Inventory | Menu |  | SGF Project
Classic | M11 | 8141 Inventory information | List | tbd | Secure MHS Reporting | SGF
Classic | M12 | 4618 Inventory list | List | Migrate | Secure MHS Reporting | SGF
Classic | M13 | 8147 Generate prescribed inven | List | Migrate | Secure MHS Reporting | SGF
Classic | M14 | 8142 Inven arts w/old LID | List | Migrate | Secure MHS Reporting | SGF
Classic | M15 | Register inven. results, sales | Write |  | SGF Project
Classic | M16 | Enter prescribed inven.result | Write |  | SGF Project
Classic | M1A | Set counting-done flag | Write |  | SGF Project
Classic | M1B | 4621 Inventory checklist | List | Migrate | Secure MHS Reporting | SGF
Classic | M1C | 8145 Inven., differences only | List | Migrate | Secure MHS Reporting | SGF
Classic | M1D | 8146 Count/inven.book.no.- ovw | List | Migrate | Secure MHS Reporting | SGF
Classic | M1E | 6700 Article movements | List | Migrate | Secure MHS Reporting | SGF
Classic | M1F | 8101 Stock movements log | List | tbd | Secure MHS Reporting | SGF
Classic | M1G | 8144 Inventory, total result | List | Migrate | Secure MHS Reporting | SGF
Classic | M1H | 4691 Create inventory trans. | List | Migrate | Secure MHS Reporting | SGF
Classic | M1I | Inventories not yet updated | Write |  | SGF Project
Classic | M1J | Delete inventory | Batch |  | SGF Project
Classic | M1K | 4620 Last inventory/article | List | Migrate | Secure MHS Reporting | SGF
Classic | M2 | Spot Inventory | Menu |  | SGF Project
Classic | M21 | 4624 Spot inventory | List | Migrate | Secure MHS Reporting | SGF
Classic | M22 | Register spot inven., sales | Write |  | SGF Project
Classic | M23 | Enter storg.loc. spot invent'y | Write |  | SGF Project
Classic | M2A | Set counting-done flag | Write |  | SGF Project
Classic | M2B | 4621 Inventory checklist | List | Migrate | Secure MHS Reporting | SGF
Classic | M2C | 8145 Inven., differences only | List | Migrate | Secure MHS Reporting | SGF
Classic | M2D | 8146 Count/inven.book.no.- ovw | List | Migrate | Secure MHS Reporting | SGF
Classic | M2E | 6700 Article movements | List | Migrate | Secure MHS Reporting | SGF
Classic | M2F | 8101 Stock movements log | List | tbd | Secure MHS Reporting | SGF
Classic | M2G | 8144 Inventory, total result | List | Migrate | Secure MHS Reporting | SGF
Classic | M2H | 4691 Create inventory trans. | List | Migrate | Secure MHS Reporting | SGF
Classic | M2I | Inventories not yet updated | Write |  | SGF Project
Classic | M2J | Delete inventory | Batch |  | SGF Project
Classic | M2K | 4620 Last inventory/article | List | Migrate | Secure MHS Reporting | SGF
Classic | M3 | Storage correction locations | Menu |  | SGF Project
Classic | M31 | Generate stor'g loc. correct'n | Write |  | SGF Project
Classic | M32 | 8141 Inventory information | List | tbd | Secure MHS Reporting | SGF
Classic | M33 | Enter corrections to stock | Write |  | SGF Project
Classic | M3A | Set counting-done flag | Write |  | SGF Project
Classic | M3B | 4621 Inventory checklist | List | Migrate | Secure MHS Reporting | SGF
Classic | M3C | 8145 Inven., differences only | List | Migrate | Secure MHS Reporting | SGF
Classic | M3D | 8146 Count/inven.book.no.- ovw | List | Migrate | Secure MHS Reporting | SGF
Classic | M3E | 6700 Article movements | List | Migrate | Secure MHS Reporting | SGF
Classic | M3F | 8101 Stock movements log | List | tbd | Secure MHS Reporting | SGF
Classic | M3G | 8144 Inventory, total result | List | Migrate | Secure MHS Reporting | SGF
Classic | M3H | 4691 Create inventory trans. | List | Migrate | Secure MHS Reporting | SGF
Classic | M3I | Inventories not yet updated | Write |  | SGF Project
Classic | M3J | Delete inventory | Batch |  | SGF Project
Classic | M3K | 4620 Last inventory/article | List | Migrate | Secure MHS Reporting | SGF
Web | OFC_O1 | SLM | Menu
Web | OFC_O11 | Maintain Sales Locations | Write
Web | OFC_O12 | Sales Location Structure | Write
Web | OFC_O13 | Work Areas | Write
Web | OFC_O14 | SLM Parameters | Write
Web | OFC_O16 | SLM Summaries | Write
Web | OFC_O17 | SLM Import | Write
Web | OFC_O2 | CPS | Menu
Web | OFC_O21 | View Pick Orders | Write
Web | OFC_O22 | Pick Orders | Write
Web | OFC_O23 | Handout Orders | Write
Web | OFC_O29 | CPS Parameters | Write
Web | OFC_O3 | Admin | Menu
Web | OFC_O31 | User administration | Write
Web | OFC_O32 | Local price administration | Write
Web | OFC_O33 | Quality Stopped Articles | Write
Web | S1 | Customer Picking Service | Menu
Web | S11 | Customer Display | Write
Web | W1 | Receive | Menu
Web | W11 | Receive Unit Load | Write
Web | W12 | Finish Unloading | Write
Web | W2 | Move | Menu
Web | W21 | Move Goods | Write
Web | W22 | Move Goods from Buffer | Write
Web | W23 | Move Goods to Buffer | Write
Web | W24 | Move Ordered Goods from Buffer | Write
Web | W25 | Move Goods to VASS | Write
Web | W26 | Move Goods From Black Box | Write
Web | W27 | Multi-Move & Data 4 Conveyor | Write
Web | W3 | Adjust Stock | Menu
Web | W31 | TT 310 Deco Transfer | Write
Web | W32 | TT 330 Quality Claims | Write
Web | W33 | TT 390 Internal Damages | Write
Web | W34 | Received Damaged | Write
Web | W35 | TT 450 Recovery-back to Stock | Write
Web | W36 | Damage Follow-up | Write
Web | W4 | View/Maintain Location(s) | Menu
Web | W41 | Maintain Sales Location | Write
Web | W42 | View Location | Write
Web | W43 | Sales Location Management | Write
Web | W44 | Notifications & Alerts | Write
Web | W5 | Stock Check | Menu
Web | W51 | Perform Stock Check | Write
Web | W52 | Perform Stock Check VASS | Write
Web | W6 | Customer Picking Service | Write
Web | W61 | Perform Pick | Write
Web | W611 | Pick Area 1 | Write
Web | W612 | Pick Area 2 | Write
Web | W613 | Pick Area 3 | Write
Web | W62 | Confirm Pick | Write
Web | W63 | Return Orders | Write

## Reference
Processes
the introduction of new ways of working
the phasing out of old ways of working
changes to existing ways of working
Organisation
new skill requirements for employees
culture changes
staffing levels
employees moving from one role to another
training needs
Technology
new computer systems
changes to existing technology systems
accommodation requirements – procuring or selling off buildings
machinery or heavy plant requirements
other equipment needs – procuring or selling off equipment
new networks or toolsets
Information
new reports
changes to existing reports or reporting systems
requirements for new data to feed into reports
project-specific data outcomes like occupancy rates if you were building a new hotel
Others
Project Milestones
Interdependencies
Stakeholder of a project
ToDo
Naming Standard
Actual start date for projects
Theoretical start date for projects
MHS TP Project / Impacting Project / Dependency Project
Note on A1: Projects change processes and introduce new ones. This area of scope covers any operational business models that will change as a result of the work that will be carried out under the programme. This can include:
Note on A6: hjoh: This area of scope covers the people changes that will result from the projects. This is a broad section and it covers everything to do with personnel from organisational culture to how many employees the company will need when the programme is complete. Examples of items that would be included in this area of scope are:
Note on A13: hjoh: Technology requirements for the programme fall into this area of scope and will typically be delivered across several projects within the programme. This area, however, covers more than just computers. It also encompasses systems, tools and other resources such as buildings. The sort of things that are included in this scope area are:
Note on A21: hjoh: This final part of scope covers the mainly intangible area of data. Information required in the new, fully transformed, organisation is noted here. These changes can be hard to establish at the beginning of the programme, so your scope statement may just say ‘new information requirements’ and these can be defined as stakeholders are engaged throughout the various projects and their reporting and information needs become known. As some examples, here is what you could include in this section:

## ProjectNames
ID | ACTUAL NAME | STATUS | NAME OF PROJECT | COMMENTS
| Support Ticket Management | also known as | New Support Ticket Mgmt
| Support Ticket Management | also known as | Case Mgmt
| Support Ticket Management | also known as | Support ticket Mgmt
| Support Ticket Management | also known as | Integrated Support Ticket Mgmt
| Support Ticket Management | also known as | Return Ticket Mgmt
| Tax Information & Calculation | has become | Remove 87 | After prestudy - Tax information & calculation was split in two.
| Tax Information & Calculation | has become | Static Retail Information | After prestudy - Tax information & calculation was split in two.
| Pricing Mgmt | also known as | Multichannel Pricing Mgmt
| Pricing Mgmt | also known as | Pricing Mgmt
| PoC | will become | Standardize Prepare Code | PoC has a milestone.
NTV35 | Secure Reporting | also known as | MHS TP Secure MHS Reporting
NTV17 | SOM | also known as | Sales Order Management
| Customer Percieved Availability | also known as | New Available to Customer
NTV30 | Customer Order Management cleanup | also known as | Customer Order Management Move Out
NTV23 | Close Cash Mgmt | also known as | Cash Mgmt
NTV26 | Credit Mgmt | also known as | Customer Financing Re-Design

## Removed Projects
GENERAL INFORMATION | [12 empty] | PRE-STUDY RELATED INFORMATION | [9 empty] | PROJECT RELATED INFORMATION | [7 empty] | SCOPE & COST |  |  | Dependencies | [8 empty] | RUNNING INFORMATION
Project | Project Status | Project Type | MHS TP Project type | Project Objective | MHST TP Objective | MHS TP Objective covered | IWOW Process | Demand function | Demand Orderer | Demand Owner | Business Project Manager | IT Project manager | MHS TP SG Approval of starting up Prestudy | Prestudy approach approved | Approved Pre-study PDI in applicable forums | Pre-study IT Blueprint conducted | SG for Prestudy appointed | Funds Secured for Prestudy | Business study conducted | Solution study conducted | Pre-study Report approved by Pre-study SG | Pre-study Report approved by MHS TP SG | Approved PDI & GPA for project in applicable forums | Approved GPA & PDI for project in Project SG | Approved PDI & GPA for projec by MHS TP SG | Project IT Blueprint conducted | Funds Secured for Project | SG for project appointed | MHS TP Representative in SG | Mapped dependencies to IWOW (all levels) | HL Cost Estimation Total Initative | HL Time Estimation total initative | Additional scope approved (If applicable) | Mapped dependencies to other projects | Mapping impact on Process conducted | Business Process Affected | Mapping impact on Organisation conducted | Roles affected | Total amount of users affected | Mapping impact on System conducted | Dependent on | Dependency type | "Gut feeling" | Milestone | Planned DP1 | Actual DP1 | TP Critical DP1 | Planned DP3 | Actual DP3 | TP Critical DP3 | Planned DP6 | Actual DP6 | TP Critical DP6 | Planned DP8 | Actual DP8 | TP Critical DP8 | Comments
iPos for Food |  | Pre-Study | Impacting Project |  |  |  | Convert visitors to happy customers... | Retail |  | Johanna Donner | [33 empty] | FY14 | [8 empty] | FY14
iPos for Food |  | Project | Impacting Project |  |  |  | Convert visitors to happy customers... |  |  | Johanna Donner
PTAG replacement |  | Pre-Study | Dependency project |  |  |  | Develop a complete home furnishing offer | Range&Supply |  | Rickard Klasson | tbd | tbd | [31 empty] | FY15 | [8 empty] | FY15 |  |  | Risk assessment of PTAG is being done during FY14
PTAG replacement |  | Project | Dependency project |  |  |  | Develop a complete home furnishing offer | Range&Supply |  | Rickard Klasson | tbd | tbd | [31 empty] | FY16 | [8 empty] | FY17? |  |  | Risk assessment of PTAG is being done during FY14
TAX Information and Calculation |  | Project | MHS TP Project |  |  |  | Perform and Report financial activities | Supporting |  |  | tbd | n/a | [31 empty] | 20150201 | [10 empty] | 20150831
Solitarie Solutions Prestudy | Closed | Pre-Study | MHS TP Project |  |  |  | Supporting |  |  | Samuel Ahlm | [34 empty] | FY14 | [8 empty] | FY14
After Sales | Remove | Pre-Study | Dependency project |  |  |  |  | Retail |  |  |  | tbd | tbd | [32 empty] | FY15 - T1 | [8 empty] | FY15 - T2
TAX Invoicing | Remove | Project | Dependency Project |  |  |  |  | Supporting |  |  |  | tbd | tbd | [32 empty] | FY15
TAX Determination | Remove | Project | Dependency Project |  |  |  |  | Supporting |  |  |  | tbd | tbd | [32 empty] | FY15
Project | Project Status | Expected Start date | Expected End date | Project Type | Project type | Project/Activity | MHS Module | Project Objective | MHST TP Objective | MHS TP Objective covered | IWOW Process | Process Owner | Process Leader | Demand function | Business Architect Manager (BAM) | IT Architect Manager (ITAM) | Chairman for SG | Sponsor for SG | Demand Orderer | Demand Owner | Business Project Manager | IT Project manager | MHS TP SG Approval of starting up Prestudy | Prestudy approach approved | Approved Pre-study PDI in applicable forums | Pre-study IT Blueprint conducted | SG for Prestudy appointed | Funds Secured for Prestudy | Business study conducted | Solution study conducted | Pre-study Report approved by Pre-study SG | Pre-study Report approved by MHS TP SG | Approved PDI & GPA for project in applicable forums | Approved GPA & PDI for project in Project SG | Approved PDI & GPA for projec by MHS TP SG | Project IT Blueprint conducted | Funds Secured for Project | SG for project appointed | MHS TP Representative in SG | Mapped dependencies to IWOW (all levels) | HL Cost Estimation Total Initative | HL Time Estimation total initative | Additional scope approved (If applicable) | Mapped dependencies to other projects | Mapping impact on Process conducted | Business Process Affected | Mapping impact on Organisation conducted | Roles affected | Total amount of users affected | Mapping impact on technology conducted | Dependent on technology | Dependency type | "Gut feeling" | Milestone | Planned DP1 | Actual DP1 | TP Critical DP1 | Planned DP3 | Actual DP3 | TP Critical DP3 | Planned DP6 | Actual DP6 | TP Critical DP6 | Planned DP8 | Actual DP8 | TP Critical DP8 | Comments
Close down HW & project | Not Started | FY20 | ? | Project | MHS TP Project | MHS Transformation Program projects |  |  | Secure that MHS can be turned of and HW closed down. |  |  |  |  | Secure IT Solutions | Per Råborg | [5 empty] | tbd | [42 empty] | ?? |  |  | Comes when MHS has been fully moved to other platforms and can be rolled out.
Customer Percieved Availability | Running | n/a | FY15 | Project | Impacting Project | Planned Business Projects | SLM |  |  |  | Plan Sales and Supply |  |  | Range&Supply |  |  | Marcus Baumgartner |  | Marcus Baumgartner |  | Ingo Bulgrin | Johan Nordin | [10 empty] | YES | YES | YES | YES | YES | YES | YES? | [15 empty] | LDI: 2013.12.02 | LDI: 2013.12.02 |  | LDI: 2014.08.27 | LDI: 2014.08.27 |  |  |  |  | LDI: 2015.08.31 | LDI: 2015.08.31 |  | Adds some logic and integration to MHS Calculations will be done in background and be fine tuned during FY15 to be the primary meassurement in FY16
Finance | Remove | FY14 | FY14 | Pre-Study | n/a | Planned Business Projects | Cash & Receipt Management, Reporting | [6 empty] | Supporting | [6 empty] | Eva Alfredsson | [45 empty] | Define the way forward in finance area, no new functionality in MHS
RDT Replacement | Remove |  |  | Project | Continuous development | Other activities impacting Tranformation Program | [7 empty] | Range&Supply | [6 empty] | tbd | [45 empty] | Need of different types of RDT and LCM of current RDTs. Current hardware is out of support in FY16
Itanium HW upgrade | Remove |  |  | Project | Continuous development | Other activities impacting Tranformation Program | [7 empty] | Secure IT Solutions | [6 empty] | tbd | [45 empty] | LCM upgrade of HW due to supportability
Auto Guided Vehicles | Remove |  |  | Project | Continuous development | Other activities impacting Tranformation Program | [7 empty] | Range&Supply | [6 empty] | -
Project | Project Status | Expected Start date | Expected End date | Project Type | Project type | Project/Activity | MHS Module | Project Objective | MHST TP Objective | MHS TP Objective covered | IWOW Process | Process Owner | Process Leader | Demand function | Business Architect Manager (BAM) | IT Architect Manager (ITAM) | Chairman for SG | Sponsor for SG | MHS TP Representative in SG | Demand Orderer | Demand Owner | Business Project Manager | IT Project manager | Anchored with applicable forums | Budget | MHS TP SG Approval of starting up Prestudy | Prestudy approach approved | Approved Pre-study PDI in applicable forums | Pre-study IT Blueprint conducted | SG for Prestudy appointed | Funds Secured for Prestudy | Business study conducted | Solution study conducted | Pre-study Report approved by Pre-study SG | Pre-study Report approved by MHS TP SG | Approved PDI & GPA for project in applicable forums | Approved GPA & PDI for project in Project SG | Approved PDI & GPA for projec by MHS TP SG | Project IT Blueprint conducted | Funds Secured for Project | SG for project appointed | Mapped dependencies to IWOW (all levels) | HL Cost Estimation Total Initative | HL Time Estimation total initative | Additional scope approved (If applicable) | Mapped dependencies to other projects | Mapping impact on Process conducted | Business Process Affected | Mapping impact on Organisation conducted | Roles affected | Total amount of users affected | Mapping impact on technology conducted | Dependent on technology | "Gut feeling" | Milestone | Planned DP1 | Actual DP1 | TP Critical DP1 | Planned DP3 | Actual DP3 | TP Critical DP3 | Planned DP6 | Actual DP6 | TP Critical DP6 | Planned DP8 | Actual DP8 | TP Critical DP8 | Comments
Pricing Management - Pre-study | Running | FY14 - T4 (august) | FY15 - T1 | Pre-Study | MHS TP Project | MHS Transformation Program projects | Range management |  |  |  | Develop a complete home furnishing offer | Kristofer Magneteg | Peter Klinkert | Range&Supply |  |  |  | Pär Gustafsson |  |  | Rikard Klasson | Elsebeth Hedberg |  | YES | YES | YES | YES | YES | YES | YES | YES | YES | [23 empty] | 2014.11.24 | [8 empty] | 2015.01.31 | 2015.01.31 | 2015.02.28
Initiative | Initiative Status | Expected Start date | Expected End date | Initiative Type | Initiative Category | Program | MHS Functionality | Project Objective | MHS TP Objective | MHS TP PDI covered | MHS TP Scope covered | Additional scope approved (If applicable) | IWOW Process | Process Owner | Process Leader | Demand function | Business Architect Manager (BAM) | IT Architect Manager (ITAM) | Chairman for SG | Sponsor for SG | MHS TP Representative in SG | Demand Orderer | Demand Owner | Business Project Manager | IT Project manager | Anchored with applicable forums | IF YES OR NO- WHICH FORUMS | Budget Secured (Clarity) | MHS TP SG Approval of starting up Prestudy | Prestudy approach approved | Approved Pre-study PDI in applicable forums | Pre-study IT Blueprint conducted | SG for Prestudy appointed | Funds Secured for Prestudy | Business study conducted | Solution study conducted | Pre-study Report approved by Pre-study SG | Pre-study Report approved by MHS TP SG | Approved PDI & GPA for project in applicable forums | Approved GPA & PDI for project in Project SG | Approved PDI & GPA for projec by MHS TP SG | Project IT Blueprint conducted | Funds Secured for Project | SG for project appointed | Mapped dependencies to IWOW (all levels) | HL Cost Estimation Total Initative | HL Time Estimation total initative | Mapped dependencies to other projects | Mapping dependencies to Process conducted | Business Process Affected | Mapping dependencies to Organisation conducted | Where in the organisation(department) does the dependency lie | Mapping dependencies to technology conducted | Dependent on technology | Process | WHEN | Organisation | Number of impacting end user | WHEN | Technology Change impact system development | WHEN | Information Change impact for user | WHEN | "Gut feeling" | Important milestone | Planned DP1 | Actual DP1 | TP Critical DP1 | Planned DP3 | Actual DP3 | TP Critical DP3 | Planned DP6 | Actual DP6 | TP Critical DP6 | Planned DP8 | Actual DP8 | TP Critical DP8 | Comments
Future Logistic in Store |  | FY14 | not defined | Project | Impacting | Planned Business |  | Develop store components, working methods and organizational set-up's to handle cash & carry and online flows and volumes in a cost efficient way | Input to SGF/SLM prestudy on future store setups and what is needed for this |  |  | n/a | Deliver service and products related to all customers | Marcus Baumgartner | Björn Westerberg | Range&Supply | Göran Johansson | Jacob Nordegren |  | Melanie van Der Toorn Vritjhoff |  |  | Sven Mertin | Thierry Shretter | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | [7 empty] | n/a | [6 empty] | YES | YES | [20 empty] | not defined |  |  | Will add new functionality, mainly to SGF and Customer Order Picking
Access Solution Prestudy | Running ? | FY14 | FY15? | Pre-Study | Dependency | Planned Business | [5 empty] | n/a | N/A |  |  | Supporting | [22 empty] | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Note on B2: hjoh: Not Started / Running / Closed
Note on C2: hjoh: Project / Pre-Study
Note on D2: hjoh: MHS TP Project / Dependency Project / Impacting Project
Note on E2: hjoh: Overall objective of the project.
Note on F2: hjoh: Objective from a MHS TP perspective
Note on G2: hjoh: MHS TP Objective Covered (Yes / no)
Note on N2: hjoh: If it is a MHS TP governed and funded initiative, has it been arppoved by the SG?
Note on O2: hjoh: Is the approach on how to deliver and the objective of the pre-study approved?
Note on R2: Link draft PDI
Note on V2: Link to SG Minutes
Note on AE2: Information in Roadmap Matrix excel
Note on AH2: Link to MHS TP SG Meeting Minutes & Link to Roadmap Matrix Excel
Note on AI2: Information in Roadmap Matrix excel
Note on B12: hjoh: Not Started / Running / Closed
Note on E12: hjoh: Project / Pre-Study
Note on F12: hjoh: MHS TP Project / Dependency Project / Impacting Project
Note on I12: hjoh: Overall objective of the project.
Note on J12: hjoh: Objective from a MHS TP perspective
Note on K12: hjoh: MHS TP Objective Covered (Yes / no)
Note on X12: hjoh: If it is a MHS TP governed and funded initiative, has it been arppoved by the SG?
Note on Y12: hjoh: Is the approach on how to deliver and the objective of the pre-study approved?
Note on AB12: Link draft PDI
Note on AF12: Link to SG Minutes
Note on AH12: heand18: Process forums and demand forums
Note on AO12: Information in Roadmap Matrix excel
Note on AR12: Link to MHS TP SG Meeting Minutes & Link to Roadmap Matrix Excel
Note on AS12: heand18: Have MHS TP been included in their dependency-mapping?
Note on AT12: heand18: P
Note on AU12: heand18: Process - mot vilka processer.
Note on AV12: heand18: Organisation = People Samköra eventuella förändringar.
Note on AW12: heand18: Logistics manager/Shop keeper - Vilka yrkesroller förändras av förändring
Note on AY12: heand18: Technology
Note on BD12: heand18: Also Current.
Note on A14: heand18: New available to customer Information taken from LDI bimonthly
Note on V14: heand18: Previous: Siv Bennhagen
Note on BD14: heand18: Plan at DP1: 2013.12.02
Note on BG14: heand18: Plan DP1: 2014.08.27
Note on B19: hjoh: Not Started / Running / Closed
Note on E19: hjoh: Project / Pre-Study
Note on F19: hjoh: MHS TP Project / Dependency Project / Impacting Project
Note on I19: hjoh: Overall objective of the project.
Note on J19: hjoh: Objective from a MHS TP perspective
Note on K19: hjoh: MHS TP Objective Covered (Yes / no)
Note on AA19: hjoh: If it is a MHS TP governed and funded initiative, has it been arppoved by the SG?
Note on AB19: hjoh: Is the approach on how to deliver and the objective of the pre-study approved?
Note on AE19: Link draft PDI
Note on AI19: Link to SG Minutes
Note on AK19: heand18: Process forums and demand forums
Note on AQ19: Information in Roadmap Matrix excel
Note on AR19: heand18: Bara MHS TP
Note on AT19: Link to MHS TP SG Meeting Minutes & Link to Roadmap Matrix ExcelbARA mhs tp
Note on AU19: heand18: Have MHS TP been included in their dependency-mapping?
Note on AV19: heand18: P
Note on AW19: heand18: Process - mot vilka processer.
Note on AX19: heand18: Organisation = People Samköra eventuella förändringar.
Note on AY19: heand18: Logistics manager/Shop keeper - Vilka yrkesroller förändras av förändring
Note on BA19: heand18: Technology
Note on BE19: heand18: Also Current.
Note on BK19: heand18: Hur ska vi fånga progress mellan DP3 till DP8!
Note on BP20: heand18: Our part needs to be delivered so we know that target will be reached FY16. Critical is
Note on B21: hjoh: Not Started / Running / Closed
Note on E21: hjoh: Project / Pre-Study
Note on F21: hjoh: MHS TP Project / Dependency Project / Impacting Project
Note on I21: hjoh: Overall objective of the project.
Note on J21: hjoh: Objective from a MHS TP perspective
Note on L21: hjoh: MHS TP Objective Covered (Yes / no)
Note on M21: Link to MHS TP SG Meeting Minutes & Link to Roadmap Matrix ExcelbARA mhs tp
Note on AA21: heand18: YES - with comment
Note on AC21: heand18: YES/NO
Note on AD21: hjoh: If it is a MHS TP governed and funded initiative, has it been arppoved by the SG?
Note on AE21: hjoh: Is the approach on how to deliver and the objective of the pre-study approved?
Note on AH21: Link draft PDI
Note on AL21: Link to SG Minutes
Note on AN21: heand18: Process forums and demand forums
Note on AT21: Information in Roadmap Matrix excel
Note on AU21: heand18: Bara MHS TP
Note on AW21: heand18: Have MHS TP been included in their dependency-mapping? For dependency and impacting projects to see if MHS TP is on the radar!
Note on AX21: heand18: P
Note on AY21: heand18: Process - mot vilka processer. Business process survey - Level 1-0 hierachy relationship. The business process is a part of a bigger process. Relaterat till Demand Function - Under demand function finns förgreningar. Vi är intresserade av affärsprocesserna relaterade till förgreningarna.
Note on AZ21: heand18: Organisation = People Samköra eventuella förändringar.
Note on BB21: heand18: Technology
Note on BD21: heand18: Performance Levels & Output The introduction of new ways of working The phasing out of old ways of working Changes to existing ways of working
Note on BF21: heand18: New skill requirements from employees Cultural changes Staffing levels Employees moving from one role to another Training needs
Note on BI21: heand18: HIGH: Complex, many dependencies to other systems/integrations etc. MEDIUM: High effort, lower complexity LOW: Lower than above New computer systems Changes to existing technology systems Accomodation requirements - Procuring and selling buildings Machinery of heavy plant requirements Other equipment needs - Procuring or selling off equipment New network or too lsets
Note on BK21: heand18: • new reports • changes to existing reports or reporting systems • requirements for new data to feed into reports • project-specific data outcomes like occupancy rates if you were building a new hotel
Note on BO21: heand18: Also Current.
Note on BU21: heand18: Hur ska vi fånga progress mellan DP3 till DP8!
Note on A22: heand18: Input SGF/SLM.

## Footnotes
ppo | project portfolio dashboard overview
ppi | project performance indicators
ldi | logistic development iniatives