## Dependency Matrix
X when rows depend on columns |  |  | X | Soft | [7 empty] | Impacting
|  |  | X | Hard | [7 empty] | MHS TP
|  |  | X | Soft & Hard | [7 empty] | Dependency
|  | NTV01 | NTV02 | NTV03 | NTV04 | NTV05 | NTV06 | NTV07 | NTV08 | NTV09 | NTV10 | NTV11 | NTV12 | NTV13 | NTV14 | NTV15 | NTV16 | NTV17 | NTV18 | NTV19 | NTV20 | NTV21 | NTV22 | NTV23 | NTV24 | NTV25 | NTV26 | NTV27 | NTV28 | NTV29 | NTV30 | NTV31 | NTV32 | NTV33 | NTV34 | NTV35 | NTV36 | NTV37 | NTV38 | NTV39 | NTV40 | NTV41 | NTV42 | NTV43 | NTV44 | NTV45 | NTV46 | NTV47 | NTV48 | NTV49 | NTV50 | NTV51 | NTV52
|  | One Cos | SAREC+ | POS Upgrade | STMS Delivery Planning | PinS | Centiro FR | Quality Deviation | New shortage handling Prestudy | One Common Replenishment | DWP | Future BI Landscape | Support Ticket Management Pre-Study | Support Ticket Management Project | Integrated Finance Platform | Traceability | Multichannel Replenishment Prestudy (range information) | SOM | Multichannel Logistic set up for stores | Multichannel Returns Management | eCom Global Rollout Project | Local integration platform Pre-Study | Local integration platform | Cash Management Pre-Study | Cash Management | Customer Financing Re-Design Pre-Study | Customer Financing Re-Design Project | Receipt Management Pre-Study | Receipt Management/Integration move out | Customer Order Management Clean-up Pre-study | Customer Order Management Clean- up | Local Pricing Management - Project | Local pricing management Pre-Study | Store Range Management move out | Reporting Pre-Study | Secure Reporting | Tax 4 orders | TAX Information and Calculation Pre-Study | Store Logistic SLM/SGF Pre-Study | Sales Location Management move out | Store Logistic Operation move out | Secure Local Solutions | Proof of Concept | MHS Initial cleanup | Standardize and prepare | Remove MHS system dependencies Pre-Study | Remove MHS system dependencies | Store Range Management Pre-study | Remove SG 87 | Static Retail Tax Information | Returns Prestudy | Returns Project | Business Credit Mgmt/RIMS
NTV01 | One COS
NTV02 | SAREC+ | bar: NTV01 to Dependency NTV52
NTV03 | POS Upgrade | bar: NTV01 to Dependency NTV52
NTV04 | STMS Delivery Planning | bar: NTV01 to Dependency NTV52
NTV05 | PinS
NTV06 | Centiro FR | bar: NTV01 to Dependency NTV52
NTV07 | Quality Deviation
NTV08 | New shortage handling Prestudy
NTV09 | One Common Replenishment | bar: NTV01 to Dependency NTV52
NTV10 | DWP
NTV11 | Future BI Landscape
NTV12 | Support Ticket Management Pre-Study
NTV13 | Support Ticket Management Project | bar: NTV01 to Dependency NTV52
NTV14 | Integrated Finance Platform
NTV15 | Tracability
NTV16 | Multichannel Replenishment Prestudy (range information)
NTV17 | SOM | bar: NTV01 to Dependency NTV52
NTV18 | Multichannel Logistic set up for stores | bar: NTV01 to Dependency NTV52
NTV19 | Multichannel Returns Management | bar: NTV01 to Dependency NTV52
NTV20 | eCom Global Rollout Project | bar: NTV01 to Dependency NTV52
NTV21 | Local integration platform Pre-Study
NTV22 | Local integration platform | bar: NTV01 to Dependency NTV52
NTV23 | Cash Management Pre-Study | bar: NTV01 to Dependency NTV52
NTV24 | Cash Management | bar: NTV01 to Dependency NTV52
NTV25 | Customer Financing Re-Design Pre-Study
NTV26 | Customer Financing Re-Design Project | bar: NTV01 to Dependency NTV52
NTV27 | Receipt Management Pre-Study
NTV28 | Receipt Management/Integration move out | bar: NTV01 to Dependency NTV52
NTV29 | Customer Order Management Clean-up Pre-study
NTV30 | Customer Order Management Clean- up | bar: NTV01 to Dependency NTV52
NTV31 | Local Pricing Management - Project | bar: NTV01 to Dependency NTV52
NTV32 | Local pricing management Pre-Study | bar: NTV01 to Dependency NTV52
NTV33 | Store Range Management move out | bar: NTV01 to Dependency NTV52
NTV34 | Reporting Pre-Study
NTV35 | Secure Reporting | bar: NTV01 to Dependency NTV52
NTV36 | Tax 4 orders
NTV37 | TAX Information and Calculation Pre-Study
NTV38 | Store Logistic SLM/SGF Pre-Study | bar: NTV01 to Dependency NTV52
NTV39 | Sales Location Management move out | bar: NTV01 to Dependency NTV52
NTV40 | Store Logistic Operation move out
NTV41 | Secure Local Solutions | bar: NTV01 to Dependency NTV52
NTV42 | Proof of Concept
NTV43 | MHS Initial cleanup
NTV44 | Standardize and prepare
NTV45 | Remove MHS system dependencies Pre-Study | bar: NTV01 to Dependency NTV52
NTV46 | Remove MHS system dependencies | bar: NTV01 to Dependency NTV52
NTV47 | Store Range Management Pre-study | bar: NTV01 to Dependency NTV52
NTV48 | Remove SG 87
NTV49 | Static Retail Tax Information
NTV50 | Returns Prestudy
NTV51 | Returns Project
NTV52 | Business Credit Mgmt/RIMS
INITIATIVE 1
INITIATIVE 2
Note on C46: Future Logistics in Store
Note on C47: Store Logistic Prestudy - SGF/SLM?

## Dependency - New
FOCUS ON TECHNOLOGY |  | Initative 1 dependent on...
Area | Initative 1
Payments & Returns | Customer Financing Re-Design Pre-Study
| Customer Financing Re-Design Project | Customer Financing Re-Design Pre-Study | Hard | Milestones | Description | 20XX-XX-XX | Local Integration Platform | Soft | Description
Business Credit Mgmt/RIMS
| Cash Management Pre-Study | [5 empty] | POS Upgrade | Soft | Description
| Cash Management | Cash Management | Hard | Milestones | Description | 20XX-XX-XX | POS Upgrade | Hard | Description | Milestones | 20XX-XX-XX | SAREC + | Hard | Description | Milestones | 20XX-XX-XX
| POS Upgrade | SOM | Soft | Description
| SAREC+ | SOM | Soft | Description
Arch Investigations
Returns Project
Finance & Reporting | Secure Reporting
Secure Local Solutions
Static Retail Tax Information
Remove SG 87
Sales Order Management | Customer Order Management Clean-up Pre-study
Customer Order Management Clean- up
SOM
PinS
eCom Global Rollout Project
Range & Pricing | Local pricing management Pre-Study
Local Pricing Management - Project
SCP | One Common Replenishment
SLM/Store Logistics | Store Logistic SLM/SGF Pre-Study
Core & IT | MHS Initial cleanup
Standardize and prepare
Proof of Concept
Local integration platform Pre-Study
Local integration platform
Note on E6: Milestones can be many things... -DP -Bus. Study - Solut.Study etc...
Note on G6: Milestone ---> - Sign-off (Resp.) - Check (Resp.) - Monitor

## Dependency - Old
Initative 2 | Initative 1 (Needs to be finished so Initative 2 can start) | Dependency type | Comment
Centiro | One COS | Hard | Resolved
Close MHS Cash Reconcilliation | Close MHS Cash Reconcilliation Pre-Study | Hard
Close MHS Cash Reconcilliation | POS Upgrade | Hard
Close MHS Cash Reconcilliation | SAREC+ | Soft
Close MHS Cash Reconcilliation Pre-Study | POS Upgrade | Soft
Credit Management | Credit management prestudy | Hard
Credit Management | Local integration platform | Soft
Credit Management Prestudy | n/a | n/a
Customer Order Management cleanup | Customer Order Management Pre-Study | Hard
Customer Order Management cleanup | OneCOS, | Hard
Customer Order Management cleanup | PinS, | Hard
Customer Order Management cleanup | Centiro FR | Hard
Customer Order Management Pre-Study | n/a | n/a
DWP | n/a | n/a
eCom Global Rollout Project | SOM | Hard
eCom Global Rollout Project | MLSS | Hard
eCom Global Rollout Project | Multichannel returns Mgmt | Hard
eCom Global Rollout Project | Tax4orders | Hard
Future BI Landscape | n/a | n/a
Future Logistic in Store | Multichannel Logistic set up for stores | Soft
Integrated Finance Platform | n/a | n/a
Local integration platform | Local integration platform Pre-Study | Hard
Local integration platform Pre-Study
Local pricing management | Multichannel returns Mgmt | Soft
Local pricing management | Local integration platform | Soft
MHS Initial cleanup | n/a | n/a
Multichannel Logistic set up for stores | SOM | Soft
Multichannel Logistic set up for stores | Future Logistics in Stores | Soft
Multichannel Replenishment Prestudy (range information) | n/a | n/a
Multichannel Returns Management | SOM | Soft
New shortage handling Prestudy | n/a | ?
One Common Replenishment | SLM | Soft
One COS | ByPass MHS | Hard
PinS | n/a | n/a
POS Upgrade | SOM | Soft | India, Romania and Croatia not part of project but needs to be moved to TP.NET before dependent projects can proceed.
Pricing Management - Pre-study | ? | ?
Local Pricing Management - Project | Local Price Management Prestudy | Hard
Local Pricing Management - Project | Local integration platform | Soft
Proof of Concept | n/a | n/a
Quality Deviation | n/a | n/a
Receipt Management Prestudy | n/a | n/a
Receipt Management/Integration move out | Receipt Management Prestudy | Hard
Receipt Management/Integration move out | Credit management | Hard
Receipt Management/Integration move out | return management | Soft
Receipt Management/Integration move out | SAREC + | Hard
Receipt Management/Integration move out | Cleanup cash reconcilliation | Hard
Remove SG 87 | n/a | n/a
Remove MHS system dependencies | Remove MHS system dependencies Pre-Study | Hard
Remove MHS system dependencies | Local Integration Platform | Hard
Remove MHS system dependencies Pre-Study | LIP | Soft
Reporting prestudy | Finance Prestudy | Soft
Sales Location Management move out | Store Logistic Prestudy | Hard
Sales Location Management move out | OCR | Hard
SAREC+ | SOM | Soft
Secure Local Solutions | Local Integration Platform, | Soft
Secure Local Solutions | Solitarie Solutions | Soft
Secure Reporting | Reporting prestudy | Hard
Secure Reporting | Local integration platform | Soft
SOM | MLSS | Soft | Mainly adds functionality to different parts of MHS, but might remove some dependecies.
SOM | Finance Prestudy | Soft
Standardize code and remove redundancy | n/a | n/a
Static Retail Price Information | n/a | n/a
STMS Delivery Planning | SOM | Soft | Their goal is to not impact MHS more then reusing existing CNS interface.
Store Logistic Operation move out | Store Logistic Prestudy | Hard
Store Logistic SLM/SGF Pre-Study | Future Logistic in Store, | Soft
Store Logistic SLM/SGF Pre-Study | SOM | Soft
Store Logistic SLM/SGF Pre-Study | STMS | Soft
Store Range Management move out | Store range mgmt prestudy | Hard
Store Range Management Prestudy | Local pricing | Soft
Support Ticket Management Prestudy | n/a | n/a
Support Ticket Management Project | Support Ticket Management Prestudy, | Hard
Support Ticket Management Project | credit management | Hard
Support Ticket Management Project | Receipt management | Soft
TAX Information and Calculation Prestudy | Integration point | Hard
Tax4orders | n/a | n/a
Traceability | n/a | n/a
Note on A15: heand18: Closed? DWP Closed in PTT
Note on A16: heand18: Information taken from PPI-folder Ingen information i PTT:n
Note on A20: heand18: FBIL
Note on A23: heand18: Hittar ej i PTT:n Kommer bli en prestudy
Note on B23: heand18: Hittar ej i PTT:n Kommer bli en prestudy
Note on A24: heand18: Hittar ej i PTT:n Kommer bli en prestudy
Note on A25: heand18: Is a part of Pricing Mgmt.
Note on A26: heand18: Is a part of Pricing Mgmt.
Note on A31: heand18: Hittar inte i PTT:n. Borde inte denna vara igång?
Note on A40: heand18: PoC has become Standardize Prepare Code but has a milestone
Note on A41: heand18: Information taken from PPI - folder
Note on A60: heand18: Sales Order Management Information taken from LDI bimonthly Kommer bli en del av eCommerce
Note on A64: heand18: csm & ship mgmt Information taken from LDI bimonthly.
Note on A76: heand18: Information taken from PDI-folder